## Consolidated
| DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT/RFQ (inc TORs & Market Research ) | Submission of ITT/RFQ to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender/RFQ | Closing date for tenders/RFQs | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
NO | Offiice of the Chief Executive Officer
Board Secretary
1 | Services | Board Evaluation | Board Evaluation ( consultancy fees) | P150 000 | P150 000 | RFQ | Done | Done | Done | Done | Done | 2026-07-03 | 17/07/2026 | 23/07/2026 | 31/07/2026 | 2026-08-05 | 18/08/2026 | N/A | 16/06/2026 | 16/06/2026 | 2026-08-07
2 | Services | Board Corporate Governance Training | Board Induction ( workshop facilities, facilitators trainining fee) | 20000 | 30000 | Micro Procurement | 2026-10-01 | N/A | N/A | 2026-10-02 | 2026-10-05 | 2026-10-06 | N/A | N/A | N/A | 2026-10-13 | N/A | N/A | 20/10/2026 | 22/10/2026 | 27/10/2026
3 | Services | Board Training | Board Training (consultancy fees, workshop facilities) | 150000 | 200000 | Micro Procurement | 2026-10-01 | N/A | N/A | 2026-10-02 | 2026-10-05 | 2026-10-06 | N/A | N/A | N/A | 2026-10-13 | N/A | N/A | 30/10/2026 | 30/10/2026 | 2026-07-11
4 | Services | Board Retreat | Board Retreat ( workshop facilities and services) | 300000 | 200000 | Micro Procurement | 2026-08-19 | N/A | N/A | 2026-08-21 | 2026-08-25 | 2026-08-28 | N/A | N/A | N/A | 2026-09-02 | N/A | N/A | 2026-09-10 | 2026-09-10 | 17/9/2026
|  |  | Total Board Secretary | 470000 | 430000
Strategy Unit
| DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT's/QPP's to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
5 | Services | Develop NHRDS | Consultancy services to develop the NHRDS | 2789898 | 2789898 | Open International Bidding | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-10 | N/A | N/A | N/A | N/A | N/A | 2025-05-26 | 2025-06-02 | 2026-08-31 | 2026-09-29
6 | Services | Develop HRDC 3rd Income Stream (Establish business development) | Develop HRDC funding strategy | 350000 | 350000 | ODB | 2027-09-10 | 2026-09-17 | 2026-09-25 | 2026-09-28 | 2026-10-22 | 2026-11-13 | 2026-11-19 | 2026-11-25 | 2026-12-01 | 2026-12-04 | 2026-12-18 | 2026-01-18 | 2027-01-26 | 2027-03-23 | 2027-03-31
7 | Services | Capacity building on foresight & futures thinking | Capacity building on foresight & futures thinking (workshop facilities, training fees) | 300000 | 300000 | RFQ | 2026-08-14 | 2026-08-18 | N/A | 2026-08-20 | 2026-08-27 | 2026-08-31 | 2026-09-03 | 2026-09-09 | 2026-09-14 | 2026-09-18 | N/A | N/A | 2026-09-20 | 2026-09-24 | 2026-09-28
8 | Services | Staff Strategy Retreat | Workshop facilities and catering services for Staff Strategy retreat | 150000 | 150000 | RFQ | 2026-06-01 | N/A | N/A | 2026-06-03 | 2026-06-05 | 2026-06-08 | N/A | N/A | N/A | 2026-06-10 | N/A | N/A | 2026-06-12 | 2026-06-12 | 2026-06-16
9 | Services | 2025-2026 Business Plan Mid-Term Review | Workshop facilities and catering services for Business Plan Mid term review | 50000 | 50000 | Micro Procurement | 2026-10-02 | N/A | N/A | 2026-10-05 | 2026-10-07 | 2026-10-12 | N/A | N/A | N/A | 2026-10-08 | N/A | N/A | 2026-10-14 | 2026-10-15 | 2026-10-19
10 | Services | Development of the HRDC Strategic Plan 2026-2031 | Consultancy services for the Development of the HRDC Strategic Plan (workshop facilities and catering Services ) | 750000 | 750000 | ODB | 2026-06-04 | 2026-06-08 | 2026-06-19 | 2026-06-19 | 2026-07-10 | 2026-07-23 | 2026-07-29 | 2026-08-03 | 2026-08-07 | 2026-08-10 | 2026-08-24 | 2026-09-11 | 2026-09-14 | 2026-10-30 | 2026-11-07
11 | Services | Development of the 2027-2028 Annual Business Plan | Develop 2027-2028 Annual Business Plan -workshop facilities and catering | 50000 | 50000 | Micro Procurement | 2026-01-05 | N/A | N/A | 2026-01-06 | 2026-01-09 | 2026-01-12 | N/A | N/A | N/A | 2026-01-14 | N/A | N/A | 2026-01-21 | 2026-01-23 | 2026-01-31
|  |  | Total Strategy Unit | 4439898 | 4439898
Internal Auditor Unit
12 | Services | Ethics Hotline (Retainer and promotion) | One Year Contract for Provision of fraud and ethics hotline | 150000 | 116307.36 | RFQ | 2027-01-14 | 2027-01-19 | N/A | 2027-01-26 | 2027-02-16 | 2027-03-03 | 2027-03-09 | 2027-03-11 | 2027-03-16 | 2027-03-19 | N/A | 2027-04-13 | 2027-03-28 | 2027-04-19 | 2027-04-26
13 | Services | Internal quality Review | Internal Assessment of the internal audit function | 300000 | 300000 | RFQ | 2026-09-01 | 2026-09-07 | N/A | 2026-09-11 | 2026-09-25 | 2026-10-12 | 2026-10-20 | 2026-10-26 | 2026-11-02 | 2026-11-06 | N/A | N/A | 2026-11-10 | 2026-11-20 | 2026-11-27
14 | Services | External Quality Review | Quality assurance of the External audit function | 500000 | 500000 | ODB | 2027-03-02 | 2027-03-11 | 2027-03-19 | 2027-02-02 | 2027-02-18 | 2027-03-11 | 2027-03-17 | 2027-03-16 | 2027-03-20 | 2027-03-25 | 2027-04-10 | 2027-04-20 | 2027-04-27 | 2027-06-26 | 2027-06-30
|  |  | Total Internal Audit | 950000 | 916307.36
Risk Unit
| Total |  | Total Risk Unit | 0 | 0
| Procurement Oversight |  | Total Procurement Oversight Unit | 0 | 0
|  |  | Total OCEO | 5859898 | 5786205.36
Offiice of the Chief Operations Officer
Marketing and Comms
15 | Services | Ghanzi Agriculture Show | Exhibition Stalls, Branding, Transport & Accomodation, and Meals for Ghanzi Agriculture Show | 31725 | 31725 | Micro Procurement | 2026-06-15 | N/A | N/A | 2025-04-16 | 2025-04-18 | 2025-04-23 | N/A | N/A | N/A | 2025-05-08 | N/A | N/A | 2025-05-21 | 2025-05-25 | 2025-05-28
16 | Services | HATAB Conference | Exhition Stalls, Branding, Transport & Accomodation, and Meals for HATAB Conference | 31500 | 31500 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-11 | 2025-04-16 | N/A | N/A | N/A | 2025-04-18 | N/A | N/A | 2025-04-24 | 2025-04-25 | 2025-04-28
17 | Services | Botswana Consumer Fair | Exhition Stalls, Branding, Transport & Accomodation, and Meals | 85800 | 85800 | Micro Procurement | 2026-07-17 | N/A | N/A | 2025-07-28 | 2025-08-01 | 2025-08-05 | N/A | N/A | N/A | 2025-08-14 | N/A | N/A | 2025-08-25 | 2025-08-31 | 2025-09-03
18 | Services | Digital Marketing (Social Media Management) | Service Provision to Manage HRDC Social Media Pages | 250000 | 250000 | RFQ | 2026-12-14 | 2025-04-17 | 2025-04-22 | 2025-04-25 | 2025-05-07 | 2025-05-15 | 2025-05-21 | 2025-05-26 | 2025-05-30 | 2025-06-03 | 2025-06-06 | 2025-06-11 | 2025-06-16 | 2025-12-17 | 2026-01-08
19 | Services | Print Media | advertising space in print media | 100000 | 100000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
20 | Services | Radio Campaign | advertising space on RADIO | 80000 | 80000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
21 | Services | Television | advertising space on TV | 50000 | 50000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
22 | Services | Outdoor Advertising | space on Outdoor Advertising | 30000 | 30000 | Micro Procurement | 2026-06-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-17 | N/A | N/A | 2025-07-30 | 2025-10-01 | 2025-10-07
23 | Services | CEO's Advocacy and Lobbying Plan Implementation | CEO's Advocacy and Lobbying Plan Stakeholder Engagement Activities | 200000 | 200000 | Micro Procurement | 2026-06-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
24 | Supplies | Board Promotional Materials | Procurement of Promotional Materials for Board Members | 50000 | 50000 | Micro Procurement | 2026-08-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-08 | N/A | N/A | 2025-07-10 | 2025-07-24 | 2025-07-31
25 | Supplies | Staff Promotional Materials | Procurement of Promotional Materials for Staff | 50000 | 50000 | Micro Procurement | 2026-08-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-08 | N/A | N/A | 2025-07-10 | 2025-07-24 | 2025-07-31
26 | Supplies | General Promotional Materials | Procurement of Promotional Materials for Staff | 100000 | 100000 | Micro Procurement | 2026-07-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
27 | Services | Podcast Services | Procurement of Podcast Services | 75000 | 75000 | Micro Procurement | 2026-08-14 | N/A | N/A | 2025-04-25 | 2025-05-07 | 2025-05-15 | N/A | N/A | N/A | 2025-05-26 | N/A | N/A | 2025-06-02 | 2025-08-01 | 2025-08-15
28 | Services | Development of Imagery | Repository for images | 75000 | 75000 | Micro Procurement | 2026-09-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2025-04-28 | 2025-05-05
29 | Services | UB Foundation | UB Foundation Sponsorship | 15000 | 15000 | Micro Procurement | 2026-10-01 | N/A | N/A | 2025-10-13 | 2025-10-16 | 2025-10-23 | N/A | N/A | N/A | 2025-11-07 | N/A | N/A | 2025-11-27 | 2025-12-01 | 2025-12-05
30 | Services | CEO and COO Hospitality | Stakeholder Engagement Activities | 50000 | 50000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-18 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
31 | Services | CSR Project | CSR Initiativse | 50000 | 50000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-18 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
32 | Services | Annual Report | Printing of Annual Report | 150000 | 150000 | RFQ | 2026-06-02 | 2025-06-05 | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | 2025-07-09 | 2025-07-11 | 2025-07-17 | 2025-07-24 | N/A | N/A | 2025-07-30 | 2025-08-07 | 2025-08-14
33 | Services | Corporate Profile | Printing of Corporate Profile | 50000 | 50000 | Micro Procurement | 2026-08-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-17 | N/A | N/A | 2025-07-30 | 2025-08-07 | 2025-08-14
34 | Services | Re-Printing | Re-printing of publications | 50000 | 50000 | Micro Procurement | 2026-09-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-17 | N/A | N/A | 2025-07-30 | 2025-08-07 | 2025-08-14
|  |  | Total Marketing and Comms | 1574025 | 1574025
|  |  | Total OCOO | 1574025 | 1574025
Department of Statistics, Research, Development and Innovation
35 | Services | Develop & implement the LMIS rollout plan | Stakeholder engagements for the launch | 50000 | 50000 | Micro Procurement | 2026-07-01 | N/A | N/A | 2026-07-10 | N/A | 2026-07-15 | N/A | N/A | N/A | 2026-07-24 | N/A | N/A | 2026-08-03 | 2026-08-10 | 2026-08-21
36 | Services |  | Facilitate system readiness activities (system pilot, data and content update) | 100000 | 100000 | Micro Procurement | 2026-05-01 | N/A | N/A | 2026-05-15 | N/A | 2026-05-19 | N/A | N/A | N/A | 2026-05-22 | N/A | N/A | 2026-05-25 | 2026-05-29 | 2026-06-05
37 | Services |  | Facilitate logistical preparations for launch (procurement of venue, live streaming & internet support, publicity & communication) | 100000 | 100000 | Micro Procurement | 2026-10-05 | N/A | N/A | 2026-10-16 | N/A | 2026-10-23 | N/A | N/A | N/A | 2026-10-30 | N/A | N/A | 2026-11-10 | 2026-11-20 | 2026-11-27
38 | Supplies |  | Procurement of LMIS promotional material | 200000 | 200000 | RFQ | 2026-09-01 | 2026-09-07 | N/A | 2026-09-11 | 2026-09-25 | 2026-10-12 | 2026-10-20 | 2026-10-26 | 2026-11-02 | 2026-11-06 | N/A | N/A | 2026-11-10 | 2026-11-20 | 2026-11-27
39 | Services |  | Conduct the handover ceremony (MoHE, MLHA, DPSM, MLGTA, MCI) | 50000 | 50000 | Micro Procurement | 2026-09-16 | N/A | N/A | 2026-09-21 | 2026-09-28 | 2026-10-09 | N/A | N/A | N/A | 2026-10-20 | N/A | N/A | 2026-11-16 | 2026-12-15 | 2026-12-18
40 | Services |  | Conduct end-user capacity building workshops (MDAs, pivate sector,local authorities)Conference facilities, travel | 100000 | 100000 | Micro Procurement | 2027-01-07 | N/A | N/A | N/A | 2027-01-16 | 2027-01-22 | N/A | N/A | N/A | 2027-01-27 | N/A | N/A | 2027-02-08 | 2027-02-26 | 2027-03-05
41 | Services |  | Conduct country-wide dissemination workshops ( conference facilities, accomodation, travel, meals) | 100000 | 100000 | Micro Procurement | 2027-01-07 | N/A | N/A | N/A | 2027-01-16 | 2027-01-22 | N/A | N/A | N/A | 2027-01-27 | N/A | N/A | 2027-02-08 | 2027-02-26 | 2027-03-05
42 | Services | Implementation of LMO/LMIS Operational Actvities | Quarter 2 - LMO Governing Body meetings (refreshments, conference facilities) | 40000 | 40000 | Micro Procurement | 2026-07-31 | N/A | N/A | 2026-07-31 | 2026-08-04 | 2026-08-07 | N/A | N/A | N/A | 2026-08-12 | N/A | N/A | 2026-08-20 | 2026-08-28 | 2026-09-01
43 | Services |  | Quarter 3 - LMO Governing Body meetings | 50000 | 50000 | Micro Procurement | 2026-10-02 | N/A | N/A | 2026-10-06 | 2026-10-12 | 2026-10-16 | N/A | N/A | N/A | 2026-10-21 | N/A | N/A | 2026-10-28 | 2026-11-02 | 2026-11-06
44 | Services |  | Quarter 4 - LMO Governing Body meetings(refreshments, conference facility) | 40000 | 40000 | Micro Procurement | 2027-02-15 | N/A | N/A | 2027-02-19 | 2027-02-22 | 2027-02-26 | N/A | N/A | N/A | 2027-03-01 | N/A | N/A | 2027-03-03 | 2027-03-10 | 2027-03-12
45 | Services |  | Collaborate with stakeholders in the production of labour market information | 100000 | 100000 | Micro Procurement | 2026-07-01 | N/A | N/A | 2026-07-10 | 2026-07-16 | 2026-07-24 | N/A | N/A | N/A | 2026-07-28 | N/A | N/A | 2026-08-03 | 2026-08-10 | 2026-08-21
46 | Services |  | LMIS Portal content development and uploading | 300000 | 300000 | RFQ | 2026-05-01 | 2026-05-15 | 2026-06-01 | 2026-06-15 | 2026-07-30 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | N/A | 2026-09-14 | 2026-09-15 | 2027-03-31 | 2027-03-31
47 | Services |  | LMIS Portal stakeholder engagement (workshop facilities, travel) | 100000 | 100000 | Micro Procurement | 2026-05-01 | N/A | N/A | 2026-05-15 | 2026-07-30 | 2026-08-07 | N/A | N/A | N/A | 2026-09-04 | N/A | N/A | 2026-09-15 | 2027-03-31 | 2027-03-31
48 | Services |  | Joint Steering Committee Retreat for JSD( accomodation, travel, conference facilities) | 150000 | 150000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-03 | 2026-08-06 | 2026-08-10 | N/A | N/A | N/A | 2026-08-14 | N/A | N/A | 2026-08-19 | 2026-08-25 | 2026-08-31
49 | Services |  | Signing of LMIS MoUs & MoAs for Jobseeker Database implementation (meals, conference facilities, décor,sound) | 220000 | 220000 | Micro Procurements | 2026-04-01 | N/A | N/A | 2026-04-08 | 2026-04-13 | 2026-04-15 | N/A | N/A | N/A | 2026-04-17 | N/A | N/A | 2026-04-21 | 2027-03-31 | 2027-03-31
50 | Services | LMIS .STAT | Conduct targeted LMIS .Stat dissemination workshops (researchers, TEI students, planners, policy advisors) | 150000 | 150000 | Micro Procurements | 2026-05-27 | N/A | N/A | 2026-06-01 | 2026-06-05 | 2026-06-08 | N/A | N/A | N/A | 2026-06-10 | N/A | N/A | 2026-06-15 | 2026-06-29 | 2026-06-30
51 | Services |  | Undertake assessments exercise with MLHA & DPSM for relevant administrative labour market data | 100000 | 100000 | Micro Procurements | 2026-05-27 | N/A | N/A | 2026-06-01 | 2026-06-05 | 2026-06-08 | N/A | N/A | N/A | 2026-06-10 | N/A | N/A | 2026-06-15 | 2026-06-29 | 2026-06-30
52 | Services |  | Capacity building for MLHA & DPSM on LMIS.STAT data structures framework | 50000 | 50000 | Micro Procurements | 2026-05-27 | N/A | N/A | 2026-06-01 | 2026-06-05 | 2026-06-08 | N/A | N/A | N/A | 2026-06-10 | N/A | N/A | 2026-06-15 | 2026-06-29 | 2026-06-30
53 | Services |  | Participation in SADC LMIS.Stat project | 112000 | 112000 | Micro Procurements | 2026-04-27 | N/A | N/A | 2026-04-30 | 2026-05-06 | 2026-05-08 | N/A | N/A | N/A | 2026-05-12 | N/A | N/A | 2026-05-18 | 2027-03-31 | 2027-03-31
54 | Services |  | Prepare & upload approved administrative records indicators in the LMIS.STAT | 300000 | 300000 | Micro Procurements | 2026-07-01 | N/A | N/A | 2026-07-03 | 2026-07-06 | 2026-07-10 | N/A | N/A | N/A | 2026-07-13 | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
55 | Services |  | Process & upload the 2024/25 BMTHS indicators in the LMIS.STAT | 50000 | 50000 | Micro Procurements | 2026-07-01 | N/A | N/A | 2026-07-03 | 2026-07-06 | 2026-07-10 | N/A | N/A | N/A | 2026-07-13 | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
56 | Services |  | Process & upload historic TEI data sets in the LMIS.STAT | 70000 | 70000 | Micro Procurements | 2026-07-01 | N/A | N/A | 2026-07-03 | 2026-07-06 | 2026-07-10 | N/A | N/A | N/A | 2026-07-13 | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
57 | Services |  | Produce a high-level labour market performance report based on LMIS.STAT | 93681 | 93681 | Micro Procurements | 2026-07-01 | N/A | N/A | 2026-07-03 | 2026-07-06 | 2026-07-10 | N/A | N/A | N/A | 2026-07-13 | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
58 | Services | Development of Skills Audit Framework - MLHA | Inception & development of data collection instruments | 100000 | 100000 | Micro Procurement | 2026-07-01 |  | N/A | 2026-07-03 | 2026-07-06 | 2026-07-08 | N/A | N/A | N/A | 2026-07-10 | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
59 | Services | Procurement of service provider for newspapers | Procurement of service provider for newspapers | 100000 | 100000 | Micro Procurements | 2026-04-01 | N/A | N/A | 2026-04-08 | 2026-04-13 | 2026-04-15 | N/A | N/A | N/A | 2026-04-17 | N/A | N/A | 2026-04-21 | 2027-03-31 | 2027-03-31
60 | Services | Produce the 2025 Tertiary Education Statistics Report | Editing of the 2025 Tertiary Education Statistics Report | 20000 | 20000 | Micro Procurements | 2026-12-01 | N/A | N/A | 2026-12-07 | 2026-12-11 | 2026-12-14 | N/A | N/A | N/A | N/A | N/A | N/A | 2027-01-06 | 2027-01-26 | 2027-03-31
61 |  |  | Printing and publishing of the 2025 Tertiary Education Statistics Report | 80000 | 80000 | Micro Procurement | 2027-01-10 | N/A | N/A | 2027-01-13 | 2027-01-16 | 2027-01-22 | N/A | N/A | N/A | 2027-01-27 | N/A | N/A | 2027-02-18 | 2027-03-04 | 2027-03-31
62 | Services | Conduct 2026/27 Census | Data Collection exercise ( venue, travel, accomodation etc) | 350000 | 350000 | Micro Procurement | 2026-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-01 | 2027-03-31 | 2027-03-31
|  | Total | Total DSRDI | 3275681 | 3275681
Department of Funding
HRDF Administration
63 | Services | Claims collection and workplace support -Palapye/Orapa | Transport and accommodation for officers- Palapye/Orapa | 50000 | 50000 | Micro Procurement | 2026-04-20 | N/A | N/A | 2026-04-20 | 2026-04-23 | 2026-04-25 | N/A | N/A | N/A | 2026-04-29 | N/A | N/A | 2026-05-03 | 2026-05-09 | 2026-05-15 | Completed
64 | Services | Claims collection and workplace support -Francistown | Transport and accommodation for officers- Francistown | 50000 | 50000 | Micro Procurement | 2026-04-20 | N/A | N/A | 2026-04-20 | 2026-04-23 | 2026-04-25 | N/A | N/A | N/A | 2026-04-29 | N/A | N/A | 2026-05-17 | 2026-05-23 | 2026-05-29
65 | Services | Claims collection and workplace support -Maun | Transport and accommodation for officers- Maun | 53000 | 53000 | Micro Procurement | 2026-04-20 | N/A | N/A | 2026-04-20 | 2026-04-23 | 2026-04-25 | N/A | N/A | N/A | 2026-04-29 | N/A | N/A | 2026-05-31 | 2026-06-06 | 2026-06-12
66 | Services | Claims collection and workplace support -Lobatse/Jwaneng | Transport and accommodation for officers- Lobatse/ Jwaneng | 58500 | 19000 | Micro Procurement | 2026-04-20 | N/A | N/A | 2026-05-12 | 2026-05-15 | 2026-05-19 | N/A | N/A | N/A | 2026-05-22 | N/A | N/A | 2026-06-08 | 2026-06-10 | 2026-06-12
67 | Services | Capacity building-breakfast meeting in Maun | Logistics for Breakfast meeting in Maun | 86271 | 86271 | Micro Procurement | 2026-08-17 | N/A | N/A | 2026-08-21 | 2026-08-25 | 2026-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-21 | 2026-09-21 | 2026-09-23
68 | Services | Capacity building-breakfast meeting S/Phikwe | Logistics for Breakfast meeting in Maun | 66180 | 66180 | Micro Procurement | 2026-08-18 | N/A | N/A | 2026-08-21 | 2026-08-25 | 2026-09-01 | N/A | N/A | N/A | 2026-09-04 | N/A | N/A | 2026-09-21 | 2026-09-21 | 2026-09-23
69 | Services | Capacity building-breakfast meeting in Francistown | Logistics for Breakfast meeting in Francistown | 61078 | 61078 | Micro Procurement | 2026-08-17 | N/A | N/A | 2026-08-21 | 2026-08-25 | 2026-09-01 | N/A | N/A | N/A | 2025-05-15 | N/A | N/A | 2026-09-23 | 2026-09-23 | 2026-09-25
70 | Services | Capacity building-breakfast meeting in Kasane | Logistics for Breakfast meeting in Kasane | 72930 | 72930 | Micro Procurement | 2026-08-17 | N/A | N/A | 2026-08-21 | 2026-08-25 | 2026-09-01 | N/A | N/A | N/A | 2025-09-04 | N/A | N/A | 2026-09-28 | 2026-09-28 | 2026-09-29
71 | Services | Capacity building-breakfast meeting in Gaborone | Logistics for Breakfast meeting in Gaborone | 80000 | 80000 | Micro Procurement | 2026-08-17 | N/A | N/A | 2026-08-21 | 2026-08-25 | 2026-09-01 | N/A | N/A | N/A | 2025-05-27 | N/A | N/A | 2026-09-29 | 2026-09-29 | 2026-09-30
72 | Services | Advertising | Purchase of Protective Clothing | 30000 | 30000 | Micro Procurement | 2026-07-10 | N/A | N/A | 2026-07-14 | 2026-07-17 | 2026-07-23 | N/A | N/A | N/A | 2026-07-27 | N/A | N/A | 2026-08-10 | 2026-08-10 | 2026-08-14
73 | Services | Advertising | Levy Payers Deadline- Adverts | 200000 | 200000 | Micro Procurement | 2027-01-12 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-11 | N/A | N/A | N/A | 2027-02-27 | N/A | N/A | 2027-03-05 | 2027-03-29 | 2027-04-10
74 | Services | Advertising | Fraud awareness adverts | 100000 | 100000 | Micro Procurement | 2027-01-12 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-11 | N/A | N/A | N/A | 2027-02-27 | N/A | N/A | 2027-03-05 | 2027-03-29 | 2027-04-10
75 | Services | AAHEFA Subscription payment | AAHEFA Subscription-Invoice | 160000 | 160000 | Micro Procurement | 2026-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-30 | 2027-01-30 | 30/02/2027
e-HRDFS Project
76 | Supplies | Design, Development and Implementation of e-HRDF System | Hardware Procurement-E-HRDF | 3000000 | 3000000 | ODB | 31/04/2025 | 2025-05-02 | 2025-05-06 | 2025-05-08 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-02 | 2025-06-04 | 2025-06-06 | 2025-06-20 | 2025-06-23 | 2025-06-24 | 2025-06-30 | 2025-06-30
77 | Supplies | e-HRDF System | Call Centre Hardware and Licenses | 1400000 | 1400000 | ODB | 2026-06-09 | 2026-06-17 | 2026-07-10 | 2026-07-14 | 2026-07-17 | 2026-07-31 | 2026-08-07 | 2026-08-12 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-11 | 2026-09-16 | 2026-11-10 | 2026-11-17
78 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Other Developer Recommended Training-Contact Centre Training | 20000 | 20000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-30 | 2026-12-04
79 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Other Developee Recommended Training(e.g Business Intelligence Reporting e.t.c) | 100000 | 80000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-30 | 2026-12-04
80 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Other Developer Recommended Training-IT Support Training | 100000 | 80000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-30 | 2026-12-04
81 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Other Developer Recommended Training- System Enhancements training | 80000 | 70000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-03-31 | 2027-03-31
82 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Activation Materials-Water Bottles, Pens, Keyholders e.t.c | 40000 | 30000 | Micro Procurement | 2026-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-08 | 2026-11-07 | 2026-12-11
83 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Activation Materials-T-Shirts (Project Teams) | 30000 | 37741 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-08 | 2026-08-29 | 2026-09-11 | N/A | N/A | N/A | 2026-10-18 | N/A | N/A | 2026-10-12 | 2026-11-07 | 2026-12-11
84 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Publicity-Display Posters/Fliers e.t.c | 20000 | 20000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-08 | 2026-08-29 | 2026-09-11 | N/A | N/A | N/A | 2026-10-18 | N/A | N/A | 2026-10-12 | 2026-11-07 | 2026-12-11
85 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Publicity-Print Media Advertising | 40000 | 30000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-01 | 2027-04-30 | 2027-05-07
86 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Social Media Advertising | 20000 | 20000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-01 | 2027-04-30 | 2027-05-07
87 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Publicity-Radio Advertising | 100000 | 50000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-01 | 2027-04-30 | 2027-05-07
88 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | Meeting Refreshments/ External Meeting Venue Expenses for e-HRDF Consultants | 150000 | 30000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-01 | 2026-11-30 | 2026-11-12
89 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals: INTERNAL SYSTEM USERS | 20000 | 20000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-01 | 2026-11-30 | 2026-12-05
90 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals: GABORONE | 40000 | 40000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
91 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport: MAUN | 60000 | 40000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
92 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport: FRANCISTOWN | 50000 | 30000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
93 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport:JWANENG/LOBATSE/ KANYE | 40000 | 20000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
94 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport:KASANE | 50000 | 40000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
95 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport: PALAPYE/SEROWE/ S. PHIKWE | 50000 | 40000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
96 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport: LETLHAKANE/ORAPA | 50000 | 40000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-12 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
97 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS | High level Capacitation Workshop e.g Facilities, Meals, accomodation, transport: GHANZI | 40000 | 40000 | Micro Procurement | 2026-11-09 | N/A | N/A | 2026-11-13 | 2026-11-18 | 2026-11-23 | N/A | N/A | N/A | 2026-11-27 | N/A | N/A | 2026-12-02 | 2027-03-31 | 2027-04-03
Non Credit Bearing Short Courses Unit
98 | Services | Capacitate NCBSC Team Members | Quality Assurance in Curriculum/Course Development | 169000 | 169000 | Micro Procurement | 2026-05-11 | N/A | N/A | 2026-05-14 | 2026-05-21 | 2026-05-26 | N/A | N/A | N/A | 2026-05-28 | N/A | N/A | 2026-06-08 | 2026-06-12 | 2026-06-19
99 | Services |  | Systems Audit in Education Environment |  |  | Micro Procurement | 2026-08-03 | N/A | N/A | 2026-08-05 | 2026-08-14 | 2026-08-19 | N/A | N/A | N/A | 2026-08-21 | N/A | N/A | 2026-08-24 | 2026-08-28 | 2026-08-31
100 | Services | Conduct Stakeholders Workshops | Conduct Stakeholders Workshops in Kasane (travel, accomodation, workshop facilities) | 60400 | 60400 | Micro Procuremen | 2026-06-22 | N/A | N/A | 2026-06-24 | 2026-07-02 | 2026-07-06 | N/A | N/A | N/A | 2026-07-09 | N/A | N/A | 2026-07-14 | 2026-07-30 | 31/07/2026
101 | Services |  | Conduct Stakeholders Workshops in Maun (travel, accomodation, workshop facilities) | 60400 | 60400 | Micro Procurement | 2026-06-22 | N/A | N/A | 2026-06-24 | 2026-07-02 | 2026-07-06 | N/A | N/A | N/A | 2026-07-09 | N/A | N/A | 2026-08-21 | 2026-08-30 | 31/08/2026
102 | Services |  | Conduct Stakeholders Workshops in F/town (travel, accomodation, workshop facilities) | 39400 | 39400 | Micro Procurement | 2026-09-07 | N/A | N/A | 2026-09-09 | 2026-09-13 | 2026-09-15 | N/A | N/A | N/A | 2025-09-18 | N/A | N/A | 2026-09-22 | 2026-09-22 | 29/09/2026
103 | Services |  | Conduct Stakeholders Workshops in Palapye (travel, accomodation, workshop facilities) | 38400 | 38400 | Micro Procurement | 2026-10-12 | N/A | N/A | 2026-10-13 | 2026-10-16 | 2026-10-21 | N/A | N/A | N/A | 2026-10-23 | N/A | N/A | 2026-10-27 | 2026-10-27 | 01/11/2026
104 | Services |  | Conduct Stakeholders Workshops in Gaborone | 50000 | 50000 | Micro Procurement | 2026-10-19 | N/A | N/A | 2026-10-20 | 2026-10-23 | 2026-10-28 | N/A | N/A | N/A | 2026-10-30 | N/A | N/A | 2026-11-10 | 2026-11-12 | 30/11/2026
105 | Services |  | Conduct Stakeholders Workshops in Jwaneng (travel, accomodation, workshop facilities) | 38400 | 38400 | Micro Procurement | 2026-10-19 | N/A | N/A | 2026-10-20 | 2026-10-23 | 2026-10-28 | N/A | N/A | N/A | 2026-10-30 | N/A | N/A | 2026-11-24 | 2026-11-24 | 30/11/2026
106 | Services | M&E to ETP's | Conduct M&E to ETPs in Kasane | 34800 | 34800 | Micro Procurement | 2026-06-22 | N/A | N/A | 2026-06-24 | 2026-07-02 | 2026-07-06 | N/A | N/A | N/A | 2026-07-09 | N/A | N/A | 2026-07-15 | 2026-07-17 | 21/07/2026
107 | Services |  | Conduct M&E to ETPs in Maun | 38500 | 38500 | Micro Procurement | 2026-06-22 | N/A | N/A | 2026-06-24 | 2026-07-02 | 2026-07-06 | N/A | N/A | N/A | 2026-07-09 | N/A | N/A | 2026-07-22 | 2026-07-24 | 21/07/2026
108 | Services |  | Conduct M&E to ETPs in F/Town | 19800 | 19800 | Micro Procurement | 2026-09-07 | N/A | N/A | 2026-09-09 | 2026-09-15 | 2026-09-17 | N/A | N/A | N/A | 2025-09-18 | N/A | N/A | 2026-09-23 | 2026-09-25 | 29/09/2026
109 | Services |  | Conduct M&E to ETPs in Palapye | 17800 | 17800 | Micro Procurement | 2026-10-12 | N/A | N/A | 2026-10-13 | 2026-10-19 | 2026-10-21 | N/A | N/A | N/A | 2026-10-23 | N/A | N/A | 2026-10-28 | 2026-10-30 | 01/11/2026
110 | Services |  | Conduct M&E to ETPs in Jwaneng | 17800 | 17800 | Micro Procuremen | 2026-10-19 | N/A | N/A | 2026-10-20 | 2026-10-23 | 2026-10-28 | N/A | N/A | N/A | 2026-10-30 | N/A | N/A | 2026-11-25 | 2026-11-27 | 30/11/2026
111 | Consultancy | Engagement of Independent Reviewers | Services of subject expert | 54000 | 54000 | Micro Procuremen | 2026-04-01 | N/A | N/A | TBD | TBD | TBD | N/A | N/A | N/A | TBD | N/A | N/A | 2026-04-01 | 2026-03-27 | 2027-03-31
112 | Services | Advertisements | Public Notice on Reviewed Guidelines & Fees | 30000 | 30000 | Micro Procurement | 2026-05-04 | N/A | N/A | 2026-05-11 | 2026-05-18 | 2026-05-20 | N/A | N/A | N/A | 2026-05-25 | N/A | N/A | 2026-06-01 | 2026-06-19 | 2026-06-30
Workplace Learning Unit
113 | Supplies | Provision of protective clothing | Protective clothing for WPL Officers | 6000 | 6000 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-15 | 2026-04-20 | 2026-04-24 | N/A | N/A | N/A | 2026-04-30 | N/A | N/A | 2026-05-04 | 2026-05-15 | 2026-05-22
115 | Services
114 | Services | Capacity Building workshop in Palapye | Capacity Building workshop in Palapye | 30500 | 30500 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-04-29 | 2026-05-04 | 2026-05-04 | 2026-05-15
115 | Services | Capacity Building workshop in Letlhakane/Orapa | Capacity Building workshop in Letlhakane/Orapa | 35500 | 35500 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-04-29 | 2026-05-06 | 2026-05-06 | 2026-05-18
116 | Services | Capacity Building workshop in Jwaneng | Capacity Building workshop in Jwaneng | 30500 | 30500 | Micro Procurement | 2026-04-27 | N/A | N/A | 2026-05-05 | 2026-05-08 | 2026-05-11 | N/A | 2026-05-12 | 2026-05-13 | 2026-05-15 | NA | 2026-05-18 | 2026-06-01 | 2026-06-01 | 2026-06-12
117 | Services | Capacity Building workshop in Tsabong | Capacity Building workshop in Tsabong | 30500 | 30500 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-05-18 | 02/06/026 | 2026-06-02 | 2026-06-15
118 | Services | Capacity Building workshop in Kang | Capacity Building workshop in Kang | 30500 | 30500 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-05-18 | 2026-06-04 | 2026-05-04 | 2026-06-16
119 | Services | Capacity Building workshop in Hukuntsi | Capacity Building workshop in Hukuntsi | 30500 | 30500 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-04-29 | 2026-05-04 | 2026-05-15 | 2026-05-22
119 | Services | Capacity Building workshop - Hukuntsi | Capacity Building workshop - Hukuntsi | 30500 | 30500 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-05-18 | 2026-06-05 | 2026-06-05 | 2026-06-17
120 | Services | Hard to reach Maun Youth Enterprises | Hard to reach Maun Youth Enterprises (Travel, accomodation, workshop facilities) | 47500 | 47500 | Micro Procurement | 2026-07-02 | N/A | N/A | 2026-07-08 | 2026-07-13 | 2026-07-14 | N/A | 2026-07-16 | 2026-07-17 | 2026-07-22 | NA | 2026-07-24 | 10/08/206 | 2026-08-14 | 2026-07-28
121 | Services | Hard to reach Ghanzi Youth Enterprises | Hard to reach Ghanzi Youth Enterprises (Travel, accomodation, workshop facilities) | 43500 | 43500 | Micro Procurement | 2026-07-02 | N/A | N/A | 2026-07-08 | 2026-07-13 | 2026-07-14 | N/A | 2026-07-16 | 2026-07-17 | 2026-07-22 | NA | 2026-07-24 | 2026-08-17 | 2026-08-21 | 2026-09-04
122 | Services | Hard to reach Tsabong Youth Enterprises | Hard to reach Tsabong Youth Enterprises | 43500 | 43500 | Micro Procurement | 2026-07-02 | N/A | N/A | 2026-07-08 | 2026-07-13 | 2026-07-14 | N/A | 2026-07-16 | 2026-07-17 | 2026-07-22 | NA | 2026-07-24 | 2026-09-07 | 2026-09-11 | 2026-09-18
123 | Services | WPL Adverts ( WSTP's and WPL Workshops) | WPL Adverts ( WSTP's and WPL Workshops) | 30000 | 30000 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2026-04-28 | 2026-04-29 | NA | 2026-04-29 | 2026-05-04 | 2026-05-29 | 2026-06-12
124 | Services | WPL Brochure | WPL Brochure | 15000 | 15000 | Micro Procurement | 2026-04-14 | N/A | N/A | 2026-04-17 | 2026-04-22 | 2026-04-24 | N/A | 2026-04-27 | 2024-04-28 | 2026-04-29 | NA | 2026-04-29 | 2026-05-11 | 2026-05-15 | 2026-05-22
125 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Selibe Phikwe (Travel, accomodation, workshop facilities) | 20000 | 20000 | Micro Procurement | 2026-10-08 | N/A | N/A | 2026-10-13 | 2026-10-14 | 2026-10-14 | N/A | 2026-10-19 | 2026-10-20 | 2026-10-21 | N/A | 2026-10-21 | 2026-11-09 | 2026-11-13 | 2026-11-28
126 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Francistown (Travel, accomodation, workshop facilities) | 20000 | 20000 | Micro Procurement | 2026-10-08 | N/A | N/A | 2026-10-13 | 2026-10-14 | 2026-10-14 | N/A | 2026-10-19 | 2026-10-20 | 2026-10-21 | N/A | 2026-11-03 | 2026-11-16 | 2026-11-20 | 2026-11-28
127 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Gaborone (Travel, accomodation, workshop facilities) | 12000 | 12000 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-04-22 | 2026-04-24 | 2026-04-29 | N/A | 2026-05-06 | 2026-05-12 | 2026-05-19 | N/A | 2026-05-22 | 2026-05-25 | 2027-02-26 | 2027-03-13
128 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Kasane (Travel, accomodation, workshop facilities) | 35000 | 35000 | Micro Procurement | 2026-10-15 | N/A | N/A | 2026-10-21 | 2026-10-23 | 2026-10-27 | N/A | 2026-10-30 | 2026-11-02 | 2026-11-03 | N/A | 2026-11-03 | 2026-11-09 | 2026-11-13 | 2026-11-27
129 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Maun (Travel, accomodation, workshop facilities) | 35000 | 35000 | Micro Procurement | 2026-10-15 | N/A | N/A | 2026-10-21 | 2026-10-23 | 2026-10-27 | N/A | 2026-10-30 | 2026-11-02 | 2026-11-03 | N/A | 2026-11-03 | 2026-11-16 | 2026-11-20 | 2026-12-11
130 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Ghanzi | 22000 | 22000 | Micro Procurement | 2026-11-02 | N/A | N/A | 2026-11-06 | 2026-11-11 | 2026-11-13 | N/A | 2026-11-18 | 2026-11-19 | 2026-11-03 | N/A | 2026-11-03 | 2026-11-23 | 2026-11-27 | 2026-12-11
131 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Shakawe (Travel, accomodation, meals) | 35000 | 35000 | Micro Procurement | 2026-11-02 | N/A | N/A | 2026-11-06 | 2026-11-11 | 2026-11-13 | N/A | 2026-11-18 | 2026-11-19 | 2026-11-24 | N/A | 2026-11-24 | 2026-12-07 | 2026-12-11 | 2027-01-15
132 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Lobatse (Travel, accomodation, meals) | 20000 | 20000 | Micro Procurement | 2027-01-04 | N/A | N/A | 2027-01-12 | 2027-01-15 | 2027-01-20 | N/A | 2027-01-22 | 2027-01-25 | 2027-01-26 | N/A | 2027-01-26 | 2027-02-01 | 2026-02-05 | 2027-02-19
133 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Palapye (Travel, accomodation, meals) | 20000 | 20000 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-10-21 | 2026-10-23 | 2026-10-27 | N/A | 2026-10-30 | 2026-11-02 | 2026-11-03 | N/A | 2026-11-03 | 2026-11-09 | 2026-12-11 | 2026-12-18
134 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Letlhakane/Orapa (Travel, accomodation, meals) | 20000 | 20000 | Micro Procurement | 2026-04-13 | N/A | N/A | 2026-10-21 | 2026-10-23 | 2026-10-27 | N/A | 2026-10-30 | 2026-11-02 | 2026-11-03 | N/A | 2026-11-03 | 2026-11-09 | 2026-12-11 | 2026-12-18
135 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Jwaneng | 20000 | 20000 | Micro Procurement | 2027-01-04 | N/A | N/A | 2027-01-12 | 2027-01-15 | 2027-01-20 | N/A | 2027-01-22 | 2027-01-25 | 2027-01-26 | N/A | 2027-01-26 | 2027-02-08 | 2026-02-12 | 2027-02-19
136 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Tsabong | 20000 | 20000 | Micro Procurement | 2027-01-18 | N/A | N/A | 2027-01-22 | 2027-01-27 | 2026-10-27 | N/A | 2027-01-28 | 2027-02-03 | 2026-02-04 | N/A | 2027-02-05 | 2027-02-15 | 2027-02-19 | 2027-03-13
137 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Kang | 20000 | 20000 | Micro Procurement | 2027-01-18 | N/A | N/A | 2027-01-22 | 2027-01-27 | 2026-10-27 | N/A | 2027-01-28 | 2027-02-03 | 2026-02-04 | N/A | 2027-02-05 | 2027-02-22 | 2027-02-26 | 2027-03-20
138 | Services | Conduct Monitoring and Evaluation to capacitated workplaces and Compliance Check | Conduct Monitoring and Evaluation Support Visit in Hukuntsi | 20000 | 20000 | Micro Procurement | 2027-01-18 | N/A | N/A | 2027-01-22 | 2027-01-27 | 2026-10-27 | N/A | 2027-01-28 | 2027-02-03 | 2026-02-04 | N/A | 2027-02-05 | 2027-03-01 | 2027-03-05 | 2027-03-20
|  |  | Total DF | 7959659 | 7597900
DHRDP-
139 | Services | Development of Botswana Skills Forecasting Model | Consultancy for Development of Botswana Skills Foorecasting Model | 2622000 | 2622000 | ODB | 2026-07-22 | 2026-08-01 | 2026-08-21 | 2026-08-24 | 2026-09-11 | 2026-10-09 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-28 | 2026-11-11 | 2026-11-16 | 2026-11-16 | 2027-03-31 | Spill over
140 | Services |  | Stakeholder Consultations (Travel, accomodation, meals) | 480398 | 480398 | Micro Procurement | 2026-11-01 | N/A | N/A | TBD | TBD | As and When | N/A | N/A | N/A | As and When | N/A | N/A | 2026-11-01 | 2027-03-31 | Spill over
141 | Services |  | Stakeholder Consultations (Travel, accomodation, meals) | 300000 | 300000 | Micro Procurement | 2026-11-01 | N/A | N/A | TBD | TBD | As and When | N/A | N/A | N/A | As and When | N/A | N/A | 2026-11-01 | 2027-03-31 | Spill over
142 | Services |  | Capacity Building (Travel, workshop facility) | 267768 | 267768 | Micro Procurement | 2026-11-01 | N/A | N/A | TBD | TBD | As and When | N/A | N/A | N/A | As and When | N/A | N/A | TBD | 2027-03-31 | Spill over
143 | Services | Review Annual Priority Skills | Data Collection for 17 sectors (Travel, accomodation, meals) | 150000 | 150000 | Micro Procurement | N/A | N/A | N/A | 2025-05-26 | 2025-05-27 | 2025-05-28 | N/A | N/A | N/A | 2025-06-29 | N/A | N/A | 2026-07-06 | 2026-11-17
144 | Services |  | Data Collection for 17 sectors (Travel, workshop facility) | 150000 | 150000 | Micro Procurement | N/A | N/A | N/A | 2025-05-26 | 2025-05-27 | 2025-05-28 | N/A | N/A | N/A | 2025-06-30 | N/A | N/A | 2026-07-06 | 2026-11-17
145 | Services |  | Stakeholder Validations Workshops (Travel, accomodation, meals) | 100000 | 100000 | Micro Procurement | N/A | N/A | N/A | 2025-06-26 | 2025-06-27 | 2025-05-27 | N/A | N/A | N/A | 2025-01-08 | N/A | N/A | 2026-11-18 | 2026-12-18
146 | Services |  | Stakeholder Validations Workshops (Travel, workshop facility) | 100000 | 100000 | Micro Procurement | N/A | N/A | N/A | 2025-07-09 | 2025-07-10 | 2025-07-11 | N/A | N/A | N/A | 2025-07-11 | N/A | N/A | 2026-11-18 | 2026-12-18
147 | Services |  | Editing and Printing | 200000 | 200000 | RFQ | N/A | N/A | N/A | 2025-05-26 | 2025-05-27 | 2025-05-28 | N/A | N/A | N/A | 2025-06-30 | N/A | N/A | 2025-06-02 | 2025-06-30
148 | Services |  | Dissemination Workshops and Conferences on Prioirity Skills Reports (Travel, accomodation, meals) | 200000 | 200000 | Micro Procurement | N/A | N/A | N/A | 2025-07-09 | 2025-07-10 | N/A | N/A | N/A | N/A | 2025-07-11 | N/A | N/A | 2026-04-01 | 2026-09-30
149 | Services |  | Dissemination Workshops and Conferences on Prioirity Skills Reports (Travel, workshop facility) | 100000 | 100000 | Micro Procurement | N/A | N/A | N/A | 2025-07-09 | 2025-07-10 | N/A | N/A | N/A | N/A | 2025-07-11 | N/A | N/A | 2026-04-01 | 2026-09-30
150 | Services | Industry-Led Capacity building (BETP) Textiles | Industry Mobilisation (Travel, accomodation, meals) | 250000 | 250000 | Micro Procurement | 2026-01-05 | N/A | N/A | As and When | As and When | N/A | N/A | N/A | N/A | As and When | N/A | N/A | 2026-05-05 | 2027-03-25 | Spill over
151 | Services |  | Industry Mobilisation (workshop facilities) | 250000 | 250000 | Micro Procurement | 2026-01-05 | N/A | N/A | As and When | 25/03/2027 | N/A | N/A | N/A | N/A | As and When | N/A | N/A | 2026-05-05 | 2027-03-25 | Spill over
152 | Services |  | Conduct Skills Gap Analysis | 300000 | 300000 | RFQ | 2026-08-03 | 2026-10-08 | N/A | 17/8/2026 | 31/08/2026 | 2026-11-09 | 18/09/2026 | 25/09/2026 | 2026-05-10 | 2026-12-10 | N/A | 23/10/2026 | 26/10/2026 | 2027-12-02 | 28/02/2027
153 | Services |  | Training Equipment | 2000000 | 2000000 | ODB | 2026-10-01 | 16/10/2026 | 30/10/2026 | 2026-11-02 | 27/11/2026 | 18/12/2026 | 2027-11-01 | 14/1/2027 | 22/01/2027 | 25/01/2027 | 2027-08-02 | 2027-11-02 | 15/02/2027 | 26/03/2027 | 31/03/2027
154 | Services |  | Select & Onboard Trainers | 250000 | 250000 | Micro Procurement | 2026-01-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-07 | 2027-03-31
155 | Services |  | Training Materials | 200000 | 200000 | Micro Procurement | 16/07/2026 | N/A | N/A | N/A | 20/07/2026 | 23/07/2026 | N/A | N/A | N/A | 25/07/2026 | N/A | N/A | 27/07/2026 | 2026-07-08 | 14/12/2026
156 | Services |  | Protective clothing | 200000 | 200000 | Micro Procurement | 16/07/2026 | N/A | N/A | N/A | 20/07/2026 | 23/07/2026 | N/A | N/A | N/A | 25/07/2026 | N/A | N/A | 27/07/2026 | 2026-07-08 | 14/12/2026
157 | Services |  | Machine consumables | 150000 | 150000 | Micro Procurement | 16/07/2026 | N/A | N/A | N/A | 20/07/2026 | 23/07/2026 | N/A | N/A | N/A | 25/07/2026 | N/A | N/A | 27/07/2026 | 2026-07-08 | 14/12/2026
158 | Services |  | Curriculum development | 200000 | 200000 | RFQ | 2026-06-01 | N/A | N/A | N/A | 2026-06-03 | 2026-06-05 | N/A | N/A | N/A | 2026-06-08 | N/A | N/A | 2026-10-06 | 15/07/2026 | 27/07/2026
159 | Services |  | Select & Onboard Trainees(orientation facilities, adverts) | 180000 | 180000 | Micro Procurement | 21/07/2026 | N/A | N/A | 23/07/2026 | N/A | 27/07/2026 | N/A | N/A | N/A | 29/07/2026 | N/A | N/A | 2026-01-08 | 21/08/2026 | 31/08/2026
160 |  |  | Launch Mentorship Programme (workshop facilities, equipment) | 1000000 | 1000000 | Tender | 2027-01-03 | 12/03/027 | 2027-01-04 | 2027-01-04 | 30/04/2027 | 14/05/207 | 21/05/2027 | 28/05/2027 | 2027-07-06 | 18/06/2027 | 25/06/2027 | 28/06/2028 | 2027-05-07 | 30/03/2028 | 2028-05-04
161 | Services | GEF SGP UNDP Community-Led Capacity Development for the Panhandle Communities Towards- Environmental Conservation and Sustainable Livelihoods | Internal Travel (travel and fuel) | 164300 | 164300 | Micro Procurement | 2026-03-08 | N/A | N/A | 2026-05-08 | N/A | 2026-07-08 | N/A | N/A | N/A | 2026-10-08 | N/A | N/A | 2026-12-08 | 31/03/2027 | 2027-04-04
162 | Services |  | Stakeholder Meetings & Workshops( veues, workshop facilities) | 55600 | 55600 | Micro Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-02 | 2027-03-31
163 | Services |  | Printing (Reports and Documentation) | 110000 | 110000 | Micro Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-03 | 2027-03-31
164 | Services | IFTDO Annual Subscrition Fees | Annual Subscription Fees for Associations | 60000 | 60000 | Micro Procurement | N/A | N/A | N/A | 2026-07-09 | N/A | N/A | N/A | N/A | N/A | 2026-07-11 | N/A | N/A | 2026-07-31 | 2027-03-31
165 | Services | Institutional Planning | Institutional Planning support to Kgatleng Brigade (RFQ-Internal travel Costs, Accommodation & incidental expenses) | 600 | 600 | Micro Procurement | 2026-07-24 | N/A | N/A | 2026-07-27 | 2026-07-31 | 2026-08-03 | N/A | N/A | N/A | 2026-08-06 | N/A |  | 2026-08-10 | 2026-08-14
166 | Services |  | Monitor implementation of Institutional Plan for Molepolole College of Education | 600 | 600 | Micro Procurement | 2026-09-04 | N/A | N/A | 2026-09-08 | 2026-09-11 | 2026-09-14 | N/A | N/A | N/A | 2026-09-15 | N/A |  | 2026-09-21 | 2026-09-25
167 | Services |  | Monitor implementation of Institutional Plan of Chobe Brigade | 17000 | 17000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-03 | 2026-08-05 | 2026-08-07 | N/A | N/A | N/A | 12//08/2026 | N/A |  | 2026-08-17 | 2026-08-21
168 | Services |  | Monitor implementation of Institutional Plan in Central District Brigades (Tutume and Nswazwi; Marobela and Marapong) | 20000 | 20000 | Micro Procurement | 2026-08-12 | N/A | N/A | 19/08/2026 | 25/08/2026 | 27/08/2026 | N/A | N/A | N/A | 2026-01-09 | N/A |  | 2026-07-09 | 2026-11-09 | 18/9/2026
169 | Services |  | Dissemination workshop for Greater Gaborone institutions | 28600 | 28600 | Micro Procurement | 2026-12-03 | N/A | N/A | 2026-12-08 | 2026-12-15 | 2026-12-17 | N/A | N/A | N/A | 2026-12-23 | N/A |  | 2027-01-11 | 2027-01-15
170 | Services |  | Dissemination workshop for Greater Francistown institutions | 40900 | 40900 | Micro Procurement | 2026-12-03 | N/A | N/A | 2026-12-08 | 2026-12-15 | 2026-12-17 | N/A | N/A | N/A | 2026-12-23 | N/A |  | 2027-01-18 | 2027-01-22
DHRDP- Student Support and Welfare
BHRDS Gaborone
171 | Services |  | Networking Dinner Decor | 67225.4386 | 67225.4386 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
172 | Services |  | Entertainment (networking dinner) | 45000 | 45000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
173 | Services |  | networking dinner MC | 7581 | 7581 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
174 | Services |  | BHRDS Fair Provision of Décor | 74950 | 74950 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
175 | Services |  | BHRDS Fair Medical Standby | 35000 | 35000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
176 | Services |  | BHRDS Fair Photography + Video Coverage | 25700 | 25700 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
177 | Services |  | BHRDS Fair token of appreciation gifts | 15000 | 15000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
178 | Services |  | BHRDS Fair Technical Equipment | 190000 | 190000 | RFQ | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-02 | 2027-02-09 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
179 |  |  | Provision of tents&chairs during the 2026 BHRDS fair in Gabs | 96790.4 | 96790.4 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
180 |  |  | internet provision during the BHRDS Fair | 50000 | 50000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
181 |  |  | BHRDS Fair Airtime for organisers (500*10 people and 100*8people) | 6000 | 6000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
182 |  |  | BHRDS Fair Catalogues | 200000 | 200000 | RFQ | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-02 | 2027-02-09 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
183 |  |  | BHRDS name tags | 1680 | 1680 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
184 |  |  | HRD Banners (BHRDS) | 29144.78 | 29144.78 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
185 |  |  | Social Media Marketing | 90000 | 90000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
186 |  |  | Radio Marketing | 70000 | 70000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
187 |  |  | Newspapers | 40000 | 40000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
188 |  |  | Social media management (3 months) | 50000 | 50000 | Micro Procurement | 2027-01-15 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-19 | N/A | N/A | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
189 |  |  | T-shirts | 95000 | 95000 | Micro Procurement | 2027-01-15 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-19 | N/A | N/A | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
190 |  |  | Golfshirts | 90000 | 90000 | Micro Procurement | 2027-01-15 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-19 | N/A | N/A | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
191 |  |  | BHRDS Merchandise (pens, drawstring bags, hats) | 80000 | 80000 | Micro Procurement | 2027-01-15 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-19 | N/A | N/A | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
192 |  |  | Overalls | 15000 | 15000 | Micro Procurement | 2027-01-15 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-19 | N/A | N/A | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
193 |  |  | Umbrellas | 15000 | 15000 | Micro Procurement | 2027-01-15 | N/A | N/A | 2027-02-02 | 2027-02-09 | 2027-02-19 | N/A | N/A | 2027-03-10 | 2027-03-12 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
194 |  |  | Bottled Water | 8000 | 8000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
195 | Services |  | Exhibitors pre and post briefing meetings | 55000 | 55000 | Micro Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-19
196 |  |  | Entertainment cost (official opening and Dinner) | 50000 | 50000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
197 | Services | BHRDS Francistown | Venue | 25000 | 25000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
198 | Services |  | Venue (cleaning, Sceurity, electricity) | 20000 | 20000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
199 | Services |  | Venue (Medical stand by ) | 7500 | 7500 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
200 | Services |  | Marquee | 100000 | 100000 | RFQ | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
201 | Services |  | Vip toilets | 10000 | 10000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
202 | Services |  | Screen for HRD vid | 18000 | 18000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
203 | Services |  | Décor | 60000 | 60000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
204 | Services |  | Catering (Water,dinner, bar limit) | 90000 | 90000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
205 | Services |  | Data collection and capturing | 3750 | 3750 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
206 | Services |  | Video and photography | 23000 | 23000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
207 | Services |  | Sound and Entertaiment | 17000 | 17000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
208 | Services |  | Transport (Car rentals, flights) | 31400 | 31400 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
209 | Services |  | Transport (Car rentals F/town) | 15000 | 15000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
210 | Services |  | Flights tickets | 10470 | 10470 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
211 | Services |  | Token of appreciation | 5000 | 5000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
212 | Services |  | Internet | 20000 | 20000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
213 | Services |  | Power connection | 18000 | 18000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
214 | Services |  | Airtime | 6000 | 6000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-03-23 | N/A | N/A | 2027-04-13 | 2027-04-16 | 2027-04-23
215 | Services | MAUN BHRDS | Venue | 40000 | 40000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
216 | Services |  | Marquee | 35000 | 35000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
217 | Services |  | Vip toilets | 5000 | 5000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
218 | Services |  | Catering (Water,dinner, bar limit) | 75500 | 75500 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
219 | Services |  | Data collection and capturing | 28500 | 28500 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
220 | Services |  | Video and photography | 10750 | 10750 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
221 | Services |  | Sound and Entertaiment | 10000 | 10000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-11
222 | Services |  | Transport for Board member | 10000 | 10000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-03-12 | 2027-03-17 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-07
223 | Services |  | Token of appreciation | 10000 | 10000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2026-04-10 | 2026-04-12 | 2026-04-14 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-07
224 | Services |  | Internet | 15000 | 15000 | Micro Procurement | 2027-03-08 | N/A | N/A | 2027-03-10 | 2027-04-12 | 2027-04-15 | N/A | N/A | N/A | 2027-04-20 | N/A | N/A | 2027-05-04 | 2027-05-06 | 2027-05-07
225 | Services | Capacity Building for Career Guidance Teachers | Travel and Accommodation | 85000 | 85000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-04 | 2026-08-07 | 2026-08-10 | N/A | N/A | N/A | 2026-08-12 | N/A | N/A | 2026-08-14 | 2026-08-17 | 2026-08-18
226 | Services | Capacity Building for Career Guidance Teachers | Venue and Catering Services | 65000 | 65000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-04 | 2026-08-07 | 2026-08-10 | N/A | N/A | N/A | 2026-08-12 | N/A | N/A | 2026-08-14 | 2026-08-17 | 2026-08-18
227 | Services | BHDRS Impact Study | Hire data Collection clerks | 90000 | 90000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-04 | 2026-08-07 | 2026-08-10 | N/A | N/A | N/A | 2026-08-12 | N/A | N/A | 2026-08-14 | 2026-08-17 | 2026-08-18
228 | Services |  | Stakeholder Consultation & Validation Workshops (venue, catering, materials, participant support) | 70000 | 70000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-04 | 2026-08-07 | 2026-08-10 | N/A | N/A | N/A | 2026-08-12 | N/A | N/A | 2026-08-14 | 2026-08-17 | 2026-08-18
229 | Services |  | Transport & Logistics (fuel, vehicle hire if required, accommodation, subsistence) | 40000 | 40000 | Micro Procurement | 2026-08-01 | N/A | N/A | 2026-08-04 | 2026-08-07 | 2026-08-10 | N/A | N/A | N/A | 2026-08-12 | N/A | N/A | 2026-08-14 | 2026-08-17 | 2026-08-18
|  |  | Total DHRDP | 2571941.6186 | 2571941.6186
DICT
230 | Supplies | IT Tablets (Surface Go) | and delivery of tablets | 180000 | 180000 | RFQ | 2026-09-10 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-10-27 | 2026-10-30 | 2026-11-03 | N/A | 2026-11-06 | 2026-11-09 | 2026-11-20 | 2026-11-27
231 | Supplies | Users Laptops | Supply and Delivery of laptops | 360000 | 360000 | ODB | 2026-07-01 | 2026-07-06 | 2026-07-14 | 2026-07-21 | 2026-07-31 | 2026-08-05 | 2026-08-13 | 2026-08-24 | 2026-08-28 | 2026-09-03 | N/A | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-24
232 | Services | SAGE VIP TOTAL SOLUTION Upgrade | system upgrade | 450000 | 450000 | ODB | 2026-08-03 | 2026-08-06 | 2026-08-14 | 2026-08-21 | 2026-09-11 | 2026-10-22 | 2026-10-28 | 2026-11-06 | 2026-11-11 | 2026-11-16 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-17 | 2027-01-08
233 | Services | HRDF Upgrade | system upgrade | 250000 | 250000 | RFQ | 2026-01-09 | 2026-04-09 | N/A | 2026-07-09 | 2026-09-21 | 2026-09-30 | 2026-09-10 | 2026-10-16 | 2026-10-23 | 2026-10-30 | N/A | 2026-09-11 | 2026-11-16 | 2026-12-16 | 2026-12-18
234 | Services | Additional Wireless Access Points | wireless access points | 300000 | 300000 | RFQ | 2026-04-17 | 2026-05-07 | 2026-05-27 | 2026-06-05 | 2026-06-08 | 2026-07-07 | 2026-07-27 | 2026-05-08 | 25/08/2026 | 2026-03-09 | 17/09/2026 | 2026-07-10 | 2026-04-12 | 26/02/2027 | 2027-09-03
235 | Services | Email Archiving Solution | Email Archiving Solution | 162186 | 162186 | RFQ | 2025-02-09 | 2025-09-22 | 2025-10-09 | 2025-10-14 | 2025-10-22 | 2025-11-20 | 2025-12-10 | 2025-12-19 | 2026-01-08 | 2026-01-19 | 2026-02-02 | 2026-02-20 | 2026-02-22 | 2026-07-14 | 2026-07-23
236 | Services | HRDC Security and Compliance audits (Pen tests etc…) | HRDC Security and Compliance audits (Pen tests etc…) | 200000 | 200000 | RFQ | 2026-09-02 | 2026-09-22 | 2026-10-12 | 2026-10-21 | 2026-10-28 | 2026-11-20 | 2026-12-10 | 2026-12-19 | 2027-01-08 | 2027-01-19 | 2027-02-02 | 2027-02-22 | 2027-04-21 | 2027-07-14 | 2027-07-23
237 | Services | Data Loss Prevention Solution | Data Loss Prevention solution | P500, 000.00 | P500, 000.00 | ODB | N/A | N/A | N/A | N/A | N/A | 2026-07-13 | 2026-08-31 | 2026-09-04 | 2026-09-18 | 2026-09-25 | 2026-10-10 | 2026-10-20 | 2026-11-01 | 2026-11-30 | 2026-12-05
238 | Services | BPM Solution | BPM Solution system | 262000 | 262000 | RFQ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-04 | 31/07/2026 | 2026-07-08
239 | Services | SLA | LMO Website | 65000 | 65000 | Micro Procurement | 2026-06-01 | N/A | N/A | 2026-06-04 | 2026-06-10 | 2026-06-15 | N/A | N/A | N/A | 2026-06-26 | N/A | N/A | 2026-07-01 | 2026-12-31 | 2027-01-07
240 | Services | SLA | HRDC Website & BHRDS Page | 60000 | 60000 | Micro Procurement | 2026-06-01 | N/A | N/A | 2026-06-04 | 2026-06-10 | 2026-06-15 | N/A | N/A | N/A | 2026-06-26 | N/A | N/A | 2026-07-01 | 2026-12-31 | 2027-01-07
241 | Services | SLA | HRDF system | 184000 | 184000 | RFQ | 2026-07-12 | 2026-07-13 | N/A | 2026-07-20 | 2026-07-31 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-03 | 2026-09-08 | N/A | N/A | 2026-09-14 | 2027-03-31 | 2027-04-07
242 | Services | SLA | UPS Batteries and Firmware Updates | 320000 | 320000 | ODB | 2027-01-11 | 2027-01-14 |  | 2026-01-20 | 2026-01-27 | 2026-01-30 | 2026-02-10 | 2027-02-15 | 2027-02-19 | 2027-02-25 | N/A | 2026-03-10 | 2026-02-17 | 2027-02-19 | 2027-02-23
243 | Services | Framework | Bitrix24 | 280000 | 280000 | RFQ | 2026-07-20 | 2026-07-22 | N/A | 2026-07-30 | 2026-08-07 | 2026-08-28 | 2026-09-04 | 2026-09-10 | 2026-09-17 | 2026-09-22 | N/A | 2026-09-25 | 2026-09-01 | 2029-08-30 | 2029-08-31
244 | Services | SLA | LMIS Annual Maintenance and Support | 200000 | 200000 | RFQ | 2026-06-07 | 2026-07-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-01 | 2027-08-30 | 2027-08-07
245 | Services | SLA | LMIS maintenance of APIs (SMS Gateway) | 50000 | 50000 | Micro Procurement | will depend on the closing and go Live of the LMIS Project
246 | Services | SLA | BPM (Budgeting) | 50000 | 50000 | Micro Procurement | 2026-07-17 | N/A | N/A | 2026-07-24 | 2026-07-29 | 2026-08-03 | N/A | N/A | N/A | 2026-08-07 | N/A | N/A | 2026-09-01 | 2028-07-31 | 2028-08-08
247 | Services | Framework | Access Control Support | 60000 | 60000 | Micro Procurement | 2025-06-05 | N/A | N/A | 2025-06-24 | 2025-06-27 | N/A | N/A | N/A | N/A | 22/09/2025 | N/A | 24/10/2025 | 23/12/2025 | 17/03/2026 | 26/03/2026
248 | Services | Framework | Backup Support and Maintenance Framework | 50000 | 50000 | Micro Procurement | 2026-05-05 | N/A | N/A | 23/06/2026 | 24/06/2026 | N/A | N/A | N/A | N/A | 21/09/2026 | N/A | 23/10/2026 | 22/12/2026 | 16/03/2027 | 25/03/2027
249 | Services | Framework | Firewall Support and Maintenance Framework | 30000 | 30000 | Micro Procurement | 2026-06-03 | N/A | N/A | 2026-06-23 | 2026-06-30 | 2026-07-24 | N/A | N/A | N/A | 2026-07-24 | N/A | 2026-07-29 | 2026-08-01 | 2026-11-30 | 2026-12-07
250 | Services | Framework | Laptops and Microsoft Surface Support and Maintenance Framework | 90000 | 90000 | Micro Procurement | 2026-08-16 | N/A | N/A | 2026-09-03 | 2026-09-09 | 2026-09-25 | N/A | N/A | N/A | 2026-10-05 | N/A | 2027-01-05 | 2027-03-04 | 2027-05-27 | 2027-07-06
251 | Services | Framework | Server Support and Maintenance Framework | 50000 | 50000 | Micro Procurement | 2026-10-12 | N/A | N/A | 2026-10-15 | 2026-10-20 | 2026-10-30 | N/A | N/A | N/A | 2026-11-06 | N/A | 2026-11-09 | 2027-01-06 | 2027-03-31 | 2027-04-09
252 | Services | Framework | Microservices Support and Maintenance Framework | 50000 | 50000 | Micro Procurement | 2026-09-04 | N/A | N/A | 2026-10-23 | 2026-10-26 | 2026-11-24 | N/A | N/A | N/A | 21/01/2027 | N/A | 24/02/2027 | 23/04/2027 | 16/07/2027 | 27/07/2027
253 | Services | Framework | Printing Solution (Support Framework) | 90000 | 90000 | Micro Procurement | 2026-07-01 | N/A | N/A | 2026-07-21 | 2026-07-31 | 2026-08-05 | N/A | N/A | N/A | 2026-09-03 | N/A | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-24
254 | Services | Subscription | Stakeholder Feedback Solution Enhancement | 90000 | 90000 | Micro Procurement | 2026-10-05 | N/A | N/A | 2026-10-22 | 2026-10-29 | 2026-11-06 | N/A | N/A | N/A | 2026-11-20 | N/A | N/A | 2027-04-01 | 2027-06-30 | 2027-07-09
255 | Services | Subscription | Absolute Endpoint Resilience | 150000 | 150000 | RFQ | 2026-04-06 | 2026-04-24 | 2026-05-14 | 2026-05-25 | 2026-05-26 | 2026-06-24 | 2026-07-14 | 2026-07-23 | 2026-08-12 | 2026-08-21 | N/A | 2026-09-24 | 2026-11-23 | 2027-02-15 | 2027-02-24
256 | Services | Subscription | Firewall(fortigate) | 90000 | 90000 | Micro Procurement | 2026-07-13 | 2026-07-16 | N/A | 2026-07-17 | 2026-07-24 | 2026-07-27 | N/A | N/A | N/A | 2026-08-06 | N/A | N/A | 2026-08-10 | N/A | 2026-08-12
257 | Services | Subscription | Email Security | 72000 | 72000 | Micro Procurement | 2026-09-10 | 2026-09-15 | N/A | 2026-09-29 | 2026-10-08 | 2026-10-12 | N/A | N/A | N/A | 2026-11-03 | N/A | 2026-11-06 | 2026-11-09 | 2026-11-07 | 2026-11-08
258 | Services | Subscription | RUCKUS Wireless | 50000 | 50000 | Micro Procurement | 2026-03-04 | N/A | N/A | 2026-04-15 | 2026-04-23 | 2026-05-22 | N/A | N/A | N/A | 2026-07-21 | N/A | 24/08/2026 | 21/10/2026 | 13/01/2027 | 22/01/2027
259 | Services | Subscription | ACCPAC | 100000 | 100000 | Micro Procurement | 2026-07-01 | N/A | N/A | 2026-07-03 | 2026-07-07 | 2026-07-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-14 | 31/07/2026 | 31/07/2026
260 | Services | Subscription | CODETWO Mail Signature | 6000 | 6000 | Micro Procurement | 2026-03-02 | N/A | N/A | 2026-03-20 | 2026-03-27 | 2026-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-16 | N/A | 2026-04-17
261 | Services | Subscription | Webroot IT Security Awareness Training | 100000 | 100000 | Micro Procurement | 2026-02-04 | 2026-02-24 | N/A | 2026-03-25 | 2026-03-30 | 2026-04-24 | N/A | N/A | N/A | 2026-05-01 | N/A | 2026-05-04 | 2026-08-23 | 2026-11-16 | 2026-12-02
262 | Services | Subscription | SYSAID ITSM Helpdesk | 200000 | 200000 | RFQ | 2026-10-05 | 2026-10-08 | N/A | 2026-10-14 | 2026-10-22 | 2026-10-30 | 2026-11-10 | 2026-11-13 | 2026-11-17 | 2026-11-20 | N/A | 2026-11-24 | 2026-11-25 | 2026-12-04 | 2026-12-18
263 | Services | Subscription | SSL Certificates (MS Exchange) | 20000 | 20000 | Micro Procurement | 2026-07-13 | N/A | N/A | 2026-07-17 | 2026-07-24 | 2026-07-27 | N/A | N/A | N/A | 2026-08-06 | N/A | N/A | 2026-08-10 | N/A | 2026-08-12
264 | Services | Subscription | Cisco Smartnet | 140000 | 140000 | RFQ | 2026-05-05 | 2026-05-25 | N/A | 2026-05-28 | 2026-06-05 | 2026-07-23 | 2026-08-12 | 2026-08-21 | 2026-10-09 | 2026-09-21 | N/A | 2026-09-25 | 2026-10-01 | 2027-03-16 | 2027-03-25
265 | Services | Subscription | Veeam | 120000 | 120000 | RFQ | 2026-07-21 | 2026-07-28 | N/A | 2026-08-03 | 2026-08-10 | 2026-09-11 | 2026-09-21 | 2026-09-29 | 2026-10-08 | 2026-10-14 | N/A | 2026-10-19 | 2026-11-01 | 2027-01-06 | 2027-10-06
266 | Services | Subscription | VMWARE - Main Site | 150000 | 150000 | RFQ | 2026-06-04 | 2026-06-24 | N/A | 2026-07-23 | 2026-07-24 | 2026-08-24 | 2026-09-11 | 2026-09-22 | 2026-10-12 | 2026-10-21 | N/A | 2026-10-24 | 2027-11-01 | 2027-04-15 | 2027-04-26
267 | Services | Subscription | VMWARE - DR Site | 150000 | 150000 | RFQ | 2026-03-04 | 2026-03-24 | N/A | 2026-04-13 | 2026-04-23 | 2026-05-22 | 2026-06-11 | 2026-06-22 | 2026-07-10 | 2026-07-21 | N/A | 2026-08-24 | 2026-10-21 | 2027-01-13 | 2027-01-22
268 | Services | Subscription | NESSUS | 95000 | 95000 | Micro Procurement | 2026-07-15 | N/A | N/A | 2026-08-10 | 2026-08-17 | 2026-09-14 | 2026-09-25 | 2026-10-05 | 2026-10-12 | 2026-10-15 | N/A | 2026-10-22 | 2026-11-01 | 2027-03-26 | 2027-04-06
269 | Services | Subscription | Gitlab Ultimate and Docker Professional | 102000 | 102000 | RFQ | 20/07/2026 | 2026-07-08 | N/A | 2026-07-09 | 2026-08-09 | 2026-07-10 | 27/10/2026 | 2026-05-11 | N/A | 2026-04-12 | N/A | 2027-07-01 | 2027-08-03 | 31/05/2027 | 2027-09-06
270 | Services | Subscription | Secondary Antirus (Symantec) | 25000 | 25000 | Micro Procurement | 2026-02-04 | N/A | N/A | 2026-03-20 | 2026-03-26 | 2026-04-24 | N/A | N/A | N/A | 2026-06-23 | N/A | 2026-07-27 | 2026-09-23 | 2026-12-16 | 2026-12-25
271 | Services | Subscription | E-Signature Solution | 15000 | 15000 | Micro Procurement | 2027-02-04 | N/A | N/A | 2027-03-20 | 2027-03-26 | 2027-04-26 | N/A | N/A | N/A | 2027-06-23 | N/A | 27/07/2027 | 23/09/2027 | 16/12/2027 | 27/12/2027
272 | Services | Subscription | Adobe Creative Suite | 20000 | 20000 | Micro Procurement | 2026-03-02 | N/A | N/A | 2026-03-20 | 2026-03-27 | 2026-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-16 | N/A | 2026-04-17
|  |  | Total DICT | 8799497.6186 | 8799497.6186
Department of Corporate Services
273 | Supplies | Procurement of HRDC Pool Vehicle | Procurement of HRDC Pool Vehicle | 800000 | 800000 | ODB | 2026-11-11 | 16/11/2026 | 27/11/2026 | 30/11/2026 | 15/12/2026 | 2027-01-26 | 2027-01-30 | 2027-02-05 | 2027-02-10 | 2027-02-12 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 2027-03-27 | 2027-03-30
274 | Supplies | Procurement of HRDC Pool Vehicle | Procurement of HRDC Pool Vehicle | 850000 | 850000 | ODB | 2026-11-11 | 16/11/2026 | 27/11/2026 | 30/11/2026 | 15/12/2026 | 2027-01-26 | 2027-01-30 | 2027-02-05 | 2027-02-10 | 2027-02-12 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 2027-03-27 | 2027-03-30
275 | Supplies | Procurement of furniture for all staff | Furniture for Staff Members | 300000 | 300000 | ODB | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-03 | 2026-08-19 | 2026-09-24 | 2026-09-29 | 2025-10-05 | 2025-10-09 | 2026-10-14 | 2026-10-28 | 30/10/2026 | 2026-11-01 | 2026-12-11 | 2026-12-15
276 | Supplies | Revamping of the Boardroom, Conference Room and CEOs Office | Revamping of the Boardroom, Conference Room and CEOs Office | 550000 | 550000 | ODB | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-03 | 2026-08-19 | 2026-09-24 | 2026-09-29 | 2025-10-05 | 2025-10-09 | 2026-10-14 | 2026-10-28 | 30/10/2026 | 2026-11-01 | 2026-12-11 | 2026-12-15
277 | Supplies | Phase 2-Design, Supply, Installation, Configuration and Commisioning of the CISCO Uniifed Communication System | Phase 2- Design, Supply, Installation, Configuration and Commisioning of the CISCO Uniifed Communication System | 1400000 | 1400000 | RDB | 2026-06-09 | 2026-06-17 | 2026-07-10 | 2026-07-14 | 2026-07-17 | 2026-07-31 | 2026-08-07 | 2026-08-12 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-11 | 2026-09-16 | 2026-11-10 | 2026-11-17
278 | Works | Installation of Cluster 1 air conditioners | Installation of Cluster 1 air conditioners | 1500000 | 1500000 | ODB | Done | Done | Done | Done | Done | Done | 2026-07-31 | 2026-07-08 | 2026-08-14 | 2026-08-20 | 2026-03-09 | 2026-09-09 | 15/9/2026 | 2026-09-11 | 2026-11-16
279 | Works | A Three Year Works Contract for Maintenance of Air conditioners, Pumps and Pipeworks | Maintenance of Air Conditioners, Pumps and Pipeworks | 420000 | 1260000 | ODB | 2026-07-13 | 2026-07-27 | 2026-08-07 | 2026-10-08 | 2026-08-28 | 2026-10-16 | 2026-10-23 | 2026-06-11 | 2026-11-11 | 2026-11-13 | 2026-11-27 | 2026-11-30 | 2026-01-12 | 2028-10-31 | 2028-11-07
280 | Works | A Three Year Works Contract for General Building maintenance | General Building Maintenance | 312000 | 900000 | ODB | 2026-07-07 | 2026-07-13 | 2026-07-24 | 2026-07-27 | 2026-08-14 | 2026-09-11 | 2026-09-18 | 2026-09-23 | 2026-10-02 | 2026-10-09 | 2026-10-23 | 2026-10-28 | 2026-01-11 | 2029-10-31 | 2029-07-11
281 | Services | A Three Services Contract for provision of Cleaning Servives | A Three Services Contract for provision of Cleaning Services | 444600 | 1333800 | ODB | 2026-07-13 | 2026-07-27 | 2026-08-07 | 2026-08-10 | 2026-08-28 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-11 | 2026-11-15 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2026-12-31 | 2028-11-07
282 | Works | A Three Year Works Contract for Provision of maintenance of electrical Installations | Maintenance of Electrical Installations | 480000 | 1440000 | ODB | 13/7/2026 | 27/07/2026 | 2026-08-07 | 2026-10-08 | 28/08/2026 | 18/09/2026 | 25/09/2026 | 2026-05-10 | 2026-09-10 | 2026-10-14 | 2026-10-23 | 2026-10-27 | 2026-01-11 | 2028-10-31 | 2028-07-11
283 | Works | Make Provision for Opening of Windows in offices | Open Windows in offices | 300000 | 300000 | ODB | 2026-09-07 | 2026-09-14 | 2026-10-02 | 2026-10-05 | 2026-10-23 | 2026-11-16 | 2026-11-20 | 2026-11-24 | 2026-11-27 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 2027-01-06 | 2027-01-30 | 2027-02-14
284 | Works | Works Project Management Services | A Three Year Contract for Provision of Project Management Consultancy Services | 400000 | 1000000 | ODB | 2027-01-14 | 2027-01-19 | 2027-01-29 | 2027-02-02 | 2027-02-16 | 2027-03-03 | 2027-03-09 | 2027-03-11 | 2027-03-16 | 2027-03-19 | 2027-04-08 | 2027-04-13 | 2027-04-20 | 2027-04-19 | 2027-04-26
285 | Works | Installation of a Water Saving System | Procurement and Installation of a water saving system | 200000 | 200000 | RFQ | 2027-01-14 | 2027-01-19 | 2027-01-29 | 2027-02-02 | 2027-02-16 | 2027-03-03 | 2027-03-09 | 2027-03-11 | 2027-03-16 | 2027-03-19 | 2027-04-08 | 2027-04-13 | 2027-04-20 | 2027-04-19 | 2027-04-26
286 | Works | Procurement of Solar Power Equipment | Procurement and Installation of Solar Power Equipment | 361403 | 361403 | ODB | 2027-01-14 | 2027-01-19 | 2027-01-29 | 2027-02-02 | 2027-02-16 | 2027-03-03 | 2027-03-09 | 2027-03-11 | 2027-03-16 | 2027-03-19 | 2027-04-08 | 2027-04-13 | 2027-04-20 | 2027-04-19 | 2027-04-26
|  |  | Total DCS | 7956600 | 11833800
Department of Human Resources
287 | Services | Skills Gap Assesment | Skills Gap Assesment | 300000 | 300000 | RFQ | 2026-10-01 | 2026-10-08 | N/A | 2026-10-16 | 2026-10-29 | 2027-01-26: 2026-10-29
288 | Services | Remuneration and Engagement Survey | Remuneration and Engagement Survey | 100000 | 100000 | RFQ | 2026-08-01 | 2025-08-08 | N/A | 2026-08-14 | 2026-08-28 | 2027-01-26: 2026-08-28; 2027-03-02: 2025-04-01; 2027-03-27: 2026-03-31
289 | Services | Implementation of culture change | Consultations, workshops | 600000 | 600000 | RFQ's/Microprocurements | 2026-09-01 | 2026-09-07 | N/A | 2026-09-10 | 2026-09-15 | 2026-09-29 | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-10-23 | N/A | N/A | 2026-11-02 | 2026-11-16 | 2026-11-23
290 | Services | Proffessional Membership Sbscriptions & CPDs | Proffessional Membership Sbscriptions & CPDs | 333710 | 333710 | RDB | 2026-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2026-03-31 | as and When
291 | Services | Office Egornomics | Procurement of Ergonomics Furniture | 150000 | 150000 | Micro procurement | 2026-04-01 | N/A | N/A | As and When |  |  | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2026-03-31
292 | Services | Employee Assistance Programme | Counselling Sessions, purchasing of wreaths for bereaved staff members | 90000 | 90000 | Micro Procurement | 2026-04-01 | N/A | N/A | As and When |  |  | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2027-03-31 | 2027-04-07
293 | Services | Commemorations & Staff Participation ( world aids day, Cancer awareness, GBV, etc) | Staff participation in commemorations procurement of banners ,promotional materials | 35000 | 35000 | Micro Procurement | 2026-09-01 | N/A | N/A | As and When |  |  | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2027-03-31 | 2027-04-07
294 | Services | End of Year Staff appreciation event ( staff motivation) | Staff Gifts, meals | 50000 | 50000 | Micro Procurement | 2026-11-02 | N/A | N/A | 2026-11-04 | 2026-11-09 | N/A | N/A | N/A | N/A | 2026-11-16 | N/A | N/A | 2026-11-17 | 2026-12-04 | 2026-12-11
295 | Services | Staff Protective Clothing | Staff Protective Clothing | 130000 | 130000 | RFQ | 2026-09-01 | 2026-09-07 | N/A | 2026-09-10 | 2026-09-15 | 2026-09-29 | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-10-23 | N/A | N/A | 2026-11-02 | 2026-11-16 | 2026-11-23
296 | Services | A Three Year Services Contract for Provision of Pension Fund Management | Provision of Pension Fund Management | 149717.29 | 149717.29 | ITT | 2026-04-01 | Done | 2026-08-28 | 2026-08-31 | 2026-09-18 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-10-11 | 2026-11-13 | 2026-11-27 | 2026-12-02 | 2026-12-03 | 2029-12-02 | 2029-12-01
297 | Services | Recruitment | Advertisement | 100000 | 100000 | Micro Procurements | 2026-04-01 | N/A | N/A | As and When |  |  | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2027-03-31 | 2027-04-07
298 | Services | Recruitment | Psychometric Assessments | 100000 | 100000 | Micro procurement | 2026-04-01 | N/A | N/A | As and When |  |  | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2027-03-31 | 2027-04-07
299 | Services | Union Meetings | Meal provision for Union Meetings | 60000 | 60000 | Micro Procurement | 2026-04-01 | N/A | N/A | As and When |  |  | N/A | N/A | N/A | As and When | N/A | N/A | 2026-04-01 | 2027-03-31 | 2026-03-31
| Total |  | Total DHR | 2198427.29 | 2198427.29
|  |  | Office of the CEO | 5859898 | 5786205.36
|  |  | Office of the COO | 1574025 | 1574025
|  |  | DSRDI | 3275681 | 3275681
|  |  | DF | 7959659 | 7597900
|  |  | HRDP | 2571941.6186 | 2571941.6186
|  |  | DICT | 8799497.6186 | 8799497.6186
|  |  | DCS | 7956600 | 11833800
|  |  | DHR | 2198427.29 | 2198427.29
|  |  | Grand Total | 40195729.5272 | 43637477.8872
|  |  | TOTAL MICRO PROCUREMENTS | 16289822.6186
Formulas:
Budget Amount BWP = SUM(E91:[Budget Amount BWP, row above])
Estimated Cost BWP = SUM(F91:[Estimated Cost BWP, row above])
Note on E12: Keitumetse BASUPI: P900 000(HRDC) P1 889 898(AFDB)
Note on N12: Keitumetse BASUPI: Vetting and procurement is handled by AfDB
Note on V106: Katlego Kelebogile BOTLHOLE: DICT TO ADVISE ON THIS PROCUREMENT ACTIVITY
Note on D191: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recruitment and orientation.
Note on G197: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incubation of entrepreneur startups

## DSRD&I (hidden)
DISCIPLINE | Project Description | Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT/RFQ (inc TORs & Market Research ) | Submission of ITT/RFQ to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services
LMIS | Develop & implement the LMIS rollout plan
|  | Stakeholder engagements for the launch | 50000 | 50000 | MPP | 2026-07-01 | 2026-07-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-03 | 2026-08-10 | 2026-08-21
|  | Facilitate system readiness activities (system pilot, data and content update) | 100000 | 100000 | MPP | 2026-05-01 | 2026-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-25 | 2026-05-29 | 2026-06-05
|  | Facilitate logistical preparations for launch (procurement of venue, live streaming & internet support, publicity & communication) | 100000 | 100000 | MPP | 2026-10-05 | 2026-10-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-10 | 2026-11-20 | 2026-11-27
|  | Procurement of LMIS promotional material | 200000 | 200000 | MPP | 2026-10-05 | 2026-10-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-10 | 2026-11-20 | 2026-11-27
|  | Conduct the handover ceremony (MoHE, MLHA, DPSM, MLGTA, MCI) | 50000 | 50000 | MPP | 2026-11-02 | 2026-11-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-16 | 2026-12-15 | 2026-12-18
|  | Conduct end-user capacity building workshops (MDAs, pivate sector,local authorities) | 100000 | 100000 | MPP | 2027-01-11 | 2027-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-02-08 | 2027-02-26 | 2027-03-05
|  | Conduct country-wide dissemination workshops | 100000 | 100000 | MPP | 2027-01-11 | 2027-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-02-08 | 2027-02-26 | 2027-03-05
LMO | Implementation of LMO/LMIS Operational Actvities
|  | Quarter 2 - LMO Governing Body meetings | 40000 | 40000 | MPP | 2026-07-31 | 2026-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-20 | 2026-08-28 | 2026-09-01
|  | Quarter 3 - LMO Governing Body meetings | 50000 | 50000 | MPP | 2026-10-14 | 2026-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-28 | 2026-11-02 | 2026-11-06
|  | Quarter 4 - LMO Governing Body meetings | 40000 | 40000 | MPP | 2027-02-15 | 2027-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-03-03 | 2027-03-10 | 2027-03-12
|  | Collaborate with stakeholders in the production of labour market information | 100000 | 100000 | MPP | 2026-07-01 | 2026-07-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-03 | 2026-08-10 | 2026-08-21
|  | LMIS Portal content development and uploading | 300000 | 300000 | QPP | 2026-05-01 | 2026-05-15 | 2026-06-01 | 2026-06-15 | 2026-07-30 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2027-03-31 | 2027-03-31
|  | LMIS Portal stakeholder engagement | 100000 | 100000 | MPP | 2026-05-01 | 2026-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-15 | 2027-03-31 | 2027-03-31
|  | Joint Steering Committee Retreat for JSD | 150000 | 150000 | MPP | 2026-08-03 | 2026-08-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-19 | 2026-08-25 | 2026-08-31
|  | Signing of LMIS MoUs & MoAs for Jobseeker Database implementation | 220000 | 220000 | MPP | 2026-04-01 | 2026-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-21 | 2027-03-31 | 2027-03-31
LMIS .STAT | LMIS .Stat Rollout | Conduct targeted LMIS .Stat dissemination workshops (researchers, TEI students, planners, policy advisors) | 150000 | 150000 | MPP | 2026-06-01 | 2026-06-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-15 | 2026-06-29 | 2026-06-30
|  | Undertake assessments exercise with MLHA & DPSM for relevant administrative labour market data | 100000 | 100000 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
|  | Capacity building for MLHA & DPSM on LMIS.STAT data structures framework | 50000 | 50000 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
|  | Participation in SADC LMIS.Stat project | 112000 | 112000 | MPP | 2026-05-04 | 2026-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-18 | 2027-03-31 | 2027-03-31
|  | Prepare & upload approved administrative records indicators in the LMIS.STAT | 300000 | 300000 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
|  | Process & upload the 2024/25 BMTHS indicators in the LMIS.STAT | 50000 | 50000 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
|  | Process & upload historic TEI data sets in the LMIS.STAT | 70000 | 70000 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
|  | Produce a high-level labour market performance report based on LMIS.STAT | 93681 | 93681 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
PROJECT NATIONAL SKILLS AUDIT | Development of Skills Audit Framework - MLHA
|  | Inception & development of data collection instruments | 100000 | 100000 | MPP | 2026-07-01 | 2026-07-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-15 | 2027-03-31 | 2027-03-31
LIBRARY MATERIAL & SUBRSCRIPTIONS | Newspapers
|  | Procurment of service provider for newspapers | 100000 | 100000 | MPP | 2026-04-01 | 2026-04-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-04 | 2027-03-31 | 2027-03-31
SERVICES | Produce the 2025 Tertiary Education Statistics Report | Editing of the 2025 Tertiary Education Statistics Report | 20000 | 20000 | Micro procurement | 2026-12-01 | N/A | N/A | 2026-12-07 | 2026-12-11 | 2026-12-14 | N/A | N/A | N/A | N/A | N/A | N/A | 2027-01-06 | 2027-01-26 | 2027-03-31
|  | Printing and publishing of the 2025 Tertiary Education Statistics Report | 80000 | 80000 | Micro procurement | 2027-01-10 | N/A | N/A | 2027-01-18 | 2027-01-30 | 2027-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2027-02-18 | 2027-03-04 | 2027-03-31
| Conduct 2026/27 Census | Data Collection exercise | 350000 | 350000 | Micro procurement | 2026-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-01 | 2027-03-31 | 2027-03-31
Total | Total |  | 3275681 | 3275681

## SPB (hidden)
| DISCIPLINE | Project Description | Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT/RFQ (inc TORs & Market Research ) | Submission of ITT/RFQ to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
NO | Offiice of the Chief Executive Officer
Department of Strategy, Policy & Business Development (DSPBD)
| DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT's/QPP's to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
5 | Services | Develop NHRDS | Consultancy services to develop the NHRDS | 2789898 | 2789898 | Open International Bidding | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-10 | N/A | N/A | N/A | N/A | N/A | 2025-05-26 | 2025-06-02 | 2026-08-31 | 2026-09-29
6 | Services | Develop HRDC 3rd Income Stream (Establish business development) | Develop HRDC funding strategy | 350000 | 350000 | ODB | 2027-01-11 | 2027-01-14 | N/A | 2027-01-15 | 2027-01-22 | 2027-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2027-01-26 | 2027-03-23 | 2027-03-31
| Services |  | Capacity building on foresight & futures thinking | 300000 | 300000 | RFQ | 2026-08-16 | 2026-08-18 |  | 2026-08-20 | 2026-08-27 | 2026-08-31 | 2026-09-02 | 2026-09-03 | 2026-09-07 | 2026-09-08 | N/A | N/A | 2026-09-20 | 2026-09-24 | 2026-09-28
| Services | Staff Strategy Retreat | Workshop facilities and catering services for Staff Strategy retreat | 150000 | 150000 | RFQ | 2026-06-02 | N/A | N/A | 2026-06-02 | 2026-06-04 | N/A | N/A | N/A | N/A | 2026-06-05 | N/A | N/A | 2026-06-12 | 2026-06-12 | 2026-06-16
| Services | 2025-2026 Business Plan Mid-Term Review | Workshop facilities and catering services for Business Plan Mid term review | 50000 | 50000 | Micro Procurement | 2026-10-05 | N/A | N/A | 2026-10-05 | 2026-10-07 | 2026-10-08 | N/A | N/A | N/A | 2026-10-08 | N/A | N/A | 2026-10-14 | 2026-10-15 | 2026-10-19
| Services | Development of the HRDC Strategic Plan 2026-2031 | Consultancy services for the Development of the HRDC Strategic Plan (workshop facilities and catering Services ) | 750000 | 750000 | RFQ/Micro Procurement | 2026-08-10 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2026-08-28 | 2026-09-01 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-09 | N/A | 2026-09-11 | 2026-09-14 | 2026-10-30 | 2026-11-07
7 | Services | Development of the 2027-2028 Annual Business Plan | Develop 2027-2028 Annual Business Plan -workshop facilities and catering | 50000 | 50000 | Micro Procurement | 2026-01-05 | N/A | N/A | 2026-01-06 | 2026-01-09 | 2026-01-12 | N/A | N/A | N/A | 2026-01-14 | N/A | N/A | 2026-01-21 | 2026-01-23 | 2026-01-31
|  |  | Total Strategy Unit | 4439898 | 4439898
Note on E5: Keitumetse BASUPI: P900 000(HRDC) P1 889 898(AFDB)
Note on N5: Keitumetse BASUPI: Vetting and procurement is handled by AfDB

## Marktn (hidden)
DISCIPLINE | Project Description | Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT/RFQ (inc TORs & Market Research ) | Submission of ITT/RFQ B:Vto POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Offiice of the Chief Operations Officer
Marketing and Comms
Services | Ghanzi Agriculture Show | Exhibition Stalls, Branding, Transport & Accomodation, and Meals for Ghanzi Agriculture Show | 31725 | 31725 | Micro Procurement | 2025-06-15 | N/A | N/A | 2025-04-16 | 2025-04-18 | 2025-04-23 | N/A | N/A | N/A | 2025-05-08 | N/A | N/A | 2025-05-21 | 2025-05-25 | 2025-05-28
Services | HATAB Conference | Exhition Stalls, Branding, Transport & Accomodation, and Meals for HATAB Conference | 31500 | 31500 | Micro Procurement | 2025-04-04 | N/A | N/A | 2025-04-10 | 2025-04-11 | 2025-04-16 | N/A | N/A | N/A | 2025-04-18 | N/A | N/A | 2025-04-24 | 2025-04-25 | 2025-04-28
Services | Botswana Consumer Fair | Exhition Stalls, Branding, Transport & Accomodation, and Meals | 85800 | 85800 | Micro Procurement | 2026-07-17 | N/A | N/A | 2025-07-28 | 2025-08-01 | 2025-08-05 | N/A | N/A | N/A | 2025-08-14 | N/A | N/A | 2025-08-25 | 2025-08-31 | 2025-09-03
Services | Digital Marketing (Social Media Management) | Service Provision to Manage HRDC Social Media Pages | 250000 | 250000 | RFQ | 2026-06-14 | 2025-04-17 | 2025-04-22 | 2025-04-25 | 2025-05-07 | 2025-05-15 | 2025-05-21 | 2025-05-26 | 2025-05-30 | 2025-06-03 | 2025-06-06 | 2025-06-11 | 2025-06-16 | 2025-12-17 | 2026-01-08
Services | Print Media | advertising space in print media | 100000 | 100000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Services | Radio Campaign | advertising space on RADIO | 80000 | 80000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Services | Television | advertising space on TV | 50000 | 50000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Services | Outdoor Advertising | space on Outdoor Advertising | 30000 | 30000 | Micro Procurement | 2026-06-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-17 | N/A | N/A | 2025-07-30 | 2025-10-01 | 2025-10-07
Services | CEO's Advocacy and Lobbying Plan Implementation | CEO's Advocacy and Lobbying Plan Stakeholder Engagement Activities | 200000 | 200000 | Micro Procurement | 2026-06-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Supplies | Board Promotional Materials | Procurement of Promotional Materials for Board Members | 50000 | 50000 | Micro Procurement | 2026-06-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-08 | N/A | N/A | 2025-07-10 | 2025-07-24 | 2025-07-31
Supplies | Staff Promotional Materials | Procurement of Promotional Materials for Staff | 50000 | 50000 | Micro Procurement | 2026-06-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-08 | N/A | N/A | 2025-07-10 | 2025-07-24 | 2025-07-31
Supplies | General Promotional Materials | Procurement of Promotional Materials for Staff | 100000 | 100000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Services | Podcast Services | Procurement of Podcast Services | 75000 | 75000 | Micro Procurement | 2026-08-14 | N/A | N/A | 2025-04-25 | 2025-05-07 | 2025-05-15 | N/A | N/A | N/A | 2025-05-26 | N/A | N/A | 2025-06-02 | 2025-08-01 | 2025-08-15
Services | Development of Imagery | Repository for images | 75000 | 75000 | Micro Procurement | 2025-07-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-22 | N/A | N/A | 2025-04-25 | 2025-04-28 | 2025-05-05
Services | UB Foundation | UB Foundation Sponsorship | 15000 | 15000 | Micro Procurement | 2026-10-01 | N/A | N/A | 2025-10-13 | 2025-10-16 | 2025-10-23 | N/A | N/A | N/A | 2025-11-07 | N/A | N/A | 2025-11-27 | 2025-12-01 | 2025-12-05
Services | CEO and COO Hospitality | Stakeholder Engagement Acttivities | 50000 | 50000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-18 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Services | CSR Project | CSR Initiativse | 50000 | 50000 | Micro Procurement | 2026-04-04 | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-04-16 | N/A | N/A | N/A | 2025-04-18 | N/A | N/A | 2025-04-25 | 2026-03-31 | 2026-04-03
Supplies | Annual Report | Printing of Annual Report | 150000 | 150000 | RFQ | 2026-08-02 | 2025-06-05 | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | 2025-07-09 | 2025-07-11 | 2025-07-17 | 2025-07-24 | N/A | N/A | 2025-07-30 | 2025-08-07 | 2025-08-14
Suplies | Corporate Profile | Printing of Corporate Profile | 50000 | 50000 | Micro Procurement | 2026-06-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-17 | N/A | N/A | 2025-07-30 | 2025-08-07 | 2025-08-14
Supplies | Re-Printing | Re-printing of publications | 50000 | 50000 | Micro Procurement | 2026-06-02 | N/A | N/A | 2025-06-17 | 2025-06-26 | 2025-07-03 | N/A | N/A | N/A | 2025-07-17 | N/A | N/A | 2025-07-30 | 2025-08-07 | 2025-08-14
|  | Total Marketing and Comms | 1574025 | 1574025
|  | Total OCOO | 1574025 | 1574025

## CS (hidden)
| DISCIPLINE | Project Description | Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT/RFQ (inc TORs & Market Research ) | Submission of ITT/RFQ to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender/RFQ | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
1 | Supplies | Procurement of HRDC Pool Vehicle | Procurement of HRDC Pool Vehicle | 800000 | 800000 | ODB | 2026-11-11 | 16/11/2026 | 27/11/2026 | 30/11/2026 | 15/12/2026 | 2027-01-26 | 2027-01-30 | 2027-02-05 | 2027-02-10 | 2027-02-12 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 2027-03-27 | 2027-03-30
2 | Supplies | Procurement of HRDC Pool Vehicle | Procurement of HRDC Pool Vehicle | 850000 | 850000 | ODB | 2026-11-11 | 16/11/2026 | 27/11/2026 | 30/11/2026 | 15/12/2026 | 2027-01-26 | 2027-01-30 | 2027-02-05 | 2027-02-10 | 2027-02-12 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 2027-03-27 | 2027-03-30
3 | Supplies | Procurement of furniture for all staff | Furniture for Staff Members | 300000 | 300000 | ODB | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-03 | 2026-08-19 | 2026-09-24 | 2026-09-29 | 2025-10-05 | 2025-10-09 | 2026-10-14 | 2026-10-28 | 30/10/2026 | 2026-11-01 | 2026-12-11 | 2026-12-15
4 | Services | Revamping of the Boardroom, Conference Room and CEOs Office | Revamping of the Boardroom, Conference Room and CEOs Office | 550000 | 550000 | ODB | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-03 | 2026-08-19 | 2026-09-24 | 2026-09-29 | 2025-10-05 | 2025-10-09 | 2026-10-14 | 2026-10-28 | 30/10/2026 | 2026-11-01 | 2026-12-11 | 2026-12-15
5 | Services | Phase 2-Design, Supply, Installation, Configuration and Commisioning of the CISCO Uniifed Communication System | Phase 2- Design, Supply, Installation, Configuration and Commisioning of the CISCO Uniifed Communication System | 1400000 | 1400000 | RDB | 2026-06-09 | 2026-06-17 | 2026-07-10 | 2026-07-14 | 2026-07-17 | 2026-07-31 | 2026-08-07 | 2026-08-12 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-11 | 2026-09-16 | 2026-11-10 | 2026-11-17
6 | Works | Installation of Cluster 1 air conditioners | Installation of Cluster 1 air conditioners | 1500000 | 1500000 | ODB | Done | Done | Done | Done | Done | Done | 31/07/2026 | 2026-07-08 | 14/08/2026 | 20/08/2026 | 2026-03-09 | 2026-09-09 | 15/9/2026 | 2026-09-11 | 16/11/2026
7 | Works | A Three Year Works Contract for Maintenance of Air conditioners, Pumps and Pipeworks | Maintenance of Air Conditioners, Pumps and Pipeworks | 420000 | 1260000 | ODB | 13/7/2026 | 27/07/2026 | 2026-08-07 | 2026-10-08 | 28/08/2026 | 16/10/2026 | 23/10/2026 | 2026-06-11 | 2026-11-11 | 13/11/2026 | 27/11/2026 | 30/11/2026 | 2026-01-12 | 31/11/2028 | 2028-11-07
8 | Works | A Three Year Works Contract for General Building maintenance | General Building Maintenance | 312000 | 900000 | ODB | 2026-07-07 | 13/07/2026 | 24/7/2026 | 27/07/2026 | 14/08/2026 | 2026-11-09 | 18/09/2026 | 23/09/2026 | 2026-02-10 | 09//10/2026 | 23/10/2026 | 28/10/2026 | 2026-01-11 | 31/10/2029 | 2029-07-11
9 | Services | A Three Services Contract for Provision of Cleaning Servives | A Three Services Contract for provision of Cleaning Services | 444600 | 1333800 | ODB | 13/7/2026 | 27/07/2026 | 2026-08-07 | 2026-10-08 | 28/08/2026 | 16/10/2026 | 23/10/2026 | 2026-06-11 | 2026-11-11 | 13/11/2026 | 27/11/2026 | 30/11/2026 | 011/12/2026 | 31/11/2028 | 2028-11-07
10 | Works | A Three Year Works Contract for Provision of maintenance of electrical Installations | Maintenance of Electrical Installations | 480000 | 1440000 | ODB | 13/7/2026 | 27/07/2026 | 2026-08-07 | 2026-10-08 | 28/08/2026 | 18/09/2026 | 25/09/2026 | 2026-05-10 | 2026-09-10 | 14/10/2026 | 23/10/2026 | 27/10/2026 | 2026-01-11 | 31/10/2028 | 2028-07-11
11 | Works | Make Provision for Opening of Windows in offices | Open Windows in offices | 300000 | 300000 | ODB | 2026-09-07 | 2026-09-14 | 2026-10-02 | 2026-10-05 | 2026-10-23 | 2026-11-16 | 2026-11-20 | 2026-11-24 | 2026-11-27 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 2027-01-06 | 2027-01-30 | 2027-02-14
12 | Works | Works Project Management Services | A Three Year Contract for Provision of Project Management Consultancy Services | 400000 | 1000000 | ODB | 14/01/2026 | 19/01/2026 | 29/01/2026 | 2026-02-02 | 16/02/2026 | 2026-03-03 | 2026-03-09 | 2026-03-11 | 2026-03-16 | 19/03/2026 | 2026-04-08 | 2026-04-13 | 2026-04-20 | 19/04/2026 | 2026-04-26
13 | Services | Installation of a Water Saving System | Procurement and Installation of a water saving system | 200000 | 200000 | RFQ | 14/01/2026 | 19/01/2026 | 29/01/2026 | 2026-02-02 | 16/02/2026 | 2026-03-03 | 2026-03-09 | 2026-03-11 | 2026-03-16 | 19/03/2026 | N/A | 24/03/2026 | 28/03/2026 | 2026-05-12 | 19/05/2026
14 | Services | Procurement of Solar Power Equipment | Procurement and Installation of Solar Power Equipment | 361403 | 361403 | ODB | 14/01/2026 | 19/01/2026 | 29/01/2026 | 2026-02-02 | 16/02/2026 | 2026-03-03 | 2026-03-09 | 2026-03-11 | 2026-03-16 | 19/03/2026 | 2026-04-08 | 2026-04-13 | 2026-04-20 | 19/04/2026 | 2026-04-26
|  |  | Total DCS | 7956600 | 11833800

## DCS (hidden)
DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender/RFQ | Closing date for tenders/RFQ | Evaluation of tender/RFQ by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO/map | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | A Three Year Services Contract for Provision of Grounds and Garden Maintenance | 3 Year Contract for Grounds and Garden Maintenance | 106330 | 106330 | ODB | 2024-04-05 | 2024-04-09 | 2024-04-26 | 2024-04-29 | 2024-05-10 | 2024-05-24 | 2024-05-31 | 2024-06-04 | 2024-06-06 | 2024-06-07 | 2024-06-21 | 2024-06-24 | 2024-07-01 | 2027-07-31 | 2027-08-07
Services | Consultancy for Provision of Audit Services | 3 Year Contract for Provision of External Audit Services for the Year 2023-2026 | 680000 | 2040000 | RDB | Done | Done | Done | Done | Done | 2024-05-08 | 2024-05-13 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 2024-06-10 | 2024-06-17 | 2024-07-01 | 2024-07-01 | 31/06/2027
Services | Provision of Project Management Services for all Works Related Services for a Period of 5 years | 5 Year Works Project Management Services | 500000 | 2500000 | ODB | 2025-12-02 | 2025-12-05 | 2025-01-10 | 2025-01-13 | 2025-01-24 | 2025-02-12 | 2025-02-12 | 2025-02-14 | 2025-02-20 | 2025-02-28 | 2025-03-14 | 2025-03-21 | 2025-04-01 | 2030-03-31 | 2030-04-10
Services | A Three Year Contract for Provision of Security Services | 3 Year Contract for Security Services | 431883 | 431883 | ODB | 2024-04-06 | 2024-04-10 | 2024-04-26 | 2024-04-29 | 2024-05-10 | 2024-06-28 | 2024-07-10 | 2024-07-12 | 2024-07-22 | 2024-07-26 | 2024-08-09 | 2024-08-16 | 2024-09-01 | 2027-09-30 | 2027-10-08
Services | Procurement of furniture for all staff | Furniture for Staff | 600000 | 600000 | ODB | 2024-08-02 | 2024-08-09 | 2024-08-23 | 2024-08-26 | 2024-09-13 | 2024-09-27 | 2024-10-03 | 2024-10-07 | 2024-10-10 | 2024-10-14 | 2024-10-25 | 2024-10-29 | 2024-11-01 | 2025-01-17 | 2024-01-24
Services | Revamp of the reception | Revamp of the reception | 400000 | 400000 | Quoutation Proposal | 2024-08-02 | 2024-08-09 | 2024-08-23 | 2024-08-26 | 2024-09-13 | 2024-09-27 | 2024-10-03 | 2024-10-07 | 2024-10-10 | 2024-10-14 | 2024-10-25 | 2024-10-29 | 2024-11-01 | 2025-01-17 | 2024-01-24
Services | Procurement of the photocopying machine | Photocopying machine | 170000 | 170000 | Quoutation Proposal | 2024-08-02 | 2024-08-09 | 2024-08-19 | 2024-08-19 | 2024-08-23 | 2024-09-03 | 2024-09-06 | 2024-09-10 | 2024-09-13 | 2024-09-16 | N/A | N/A | 2024-09-23 | 2024-10-18 | 2024-10-25
Supplies | Office Cleaning and Supplies | Monthly Procurement of Domestic Supplies | 651805 | 651805 | Micro Procurement | Monthly | N/A | N/A | Monthly | N/A | N/A | N/A | N/A | N/A | Monthly | N/A | N/A | 2024-04-01 | 2025-03-31 | Monthly
Supplies | Stationery | Quartely Procurement of Stationery | 800000 | 800000 | Micro Procurement | Quartely | N/A | N/A | Qurtely | N/A | N/A | N/A | N/A | N/A | Quartely | N/A | N/A | 2024-04-01 | 2025-03-31 | Quartely
Services | Procurement of the Telecommunication management system | Telecommunication management system | 800000 | 800000 | RDB | 2024-06-17 | 2024-06-21 | 2024-07-05 | 2024-07-08 | 2024-08-02 | 2024-08-27 | 2024-09-11 | 2024-09-17 | 2024-09-20 | 2024-09-25 | 2024-10-11 | 2024-10-18 | 2024-10-21 | 2024-12-13 | 2024-12-20
Works | Provision of Waterproofing Services and its associated building maintenance | Waterproofing Services | 1200000 | 1200000 | ODB | 2024-04-16 | 2024-04-19 | 2024-05-03 | 2024-05-06 | 2024-05-24 | 2024-06-18 | 2024-06-28 | 2024-07-04 | 2024-07-09 | 2024-07-12 | 2024-07-30 | 2024-08-02 | 2024-08-07 | 2027-09-18 | 2027-09-27
Works | Installation of Cluster 1 air conditioners | Installation of Cluster 1 air conditioners | 1700000 | 1700000 | ODB | 2024-04-30 | 2024-05-07 | 2024-05-17 | 2024-05-20 | 2024-06-07 | 2024-06-28 | 2024-07-05 | 2024-07-10 | 2024-07-12 | 2024-07-19 | 2024-08-02 | 2024-08-09 | 2024-08-12 | 2024-09-27 | 2024-10-04
Works | General Building Maintenance | General Building Maintenance | 240000 | 240000 | ODB | 2024-05-17 | 2024-05-22 | 2024-05-31 | 2024-06-03 | 2024-06-19 | 2024-07-12 | 2024-07-19 | 2024-07-23 | 2024-07-25 | 2024-07-29 | 2024-08-09 | 2024-08-16 | 2024-09-01 | 2027-09-30 | 2027-10-08
Works | A Three Year Works Contract for Provision of maintenance of electrical installations | Maintenance of Electrical Installations | 480000 | 480000 | ODB | 2024-05-22 | 2024-05-30 | 2024-06-17 | 2024-06-21 | 2024-07-12 | 2024-07-31 | 2024-08-06 | 2024-08-08 | 2024-08-12 | 2024-08-14 | 2024-08-28 | 2024-09-04 | 2024-10-01 | 2027-09-30 | 2027-10-08
Works | Replacement of Carpet and Tiles | Replacement of Carpet and Tiles | 350000 | 350000 | Quotation proposal | 2024-07-05 | 2024-07-11 | N/A | 2024-07-23 | 2024-07-31 | 2024-08-12 | 2024-08-20 | 2024-08-22 | 2024-08-28 | 2024-08-30 | N/A | N/A | 2024-09-04 | 2024-09-25 | 2024-10-07
Works | Open Windows | Open Windows | 400000 | 400000 | Quotation proposal | 2024-09-09 | 2024-09-16 | N/A | 2024-09-23 | 2024-10-11 | 2024-10-30 | 2024-11-11 | 2024-11-14 | 2024-11-19 | 2024-11-22 | N/A | 2024-11-25 | 2024-11-26 | 2024-12-17 | 2025-01-06
Works | Installation of porta cabins | Relocation and Installation of porta cabins | 250000 | 250000 | Quoutation Proposal | 2024-10-14 | 2024-10-17 | N/A | 2024-10-28 | 2024-11-01 | 2024-11-08 | 2024-11-14 | 2024-11-15 | 2024-11-20 | 2024-11-22 | N/A | 2024-11-28 | 2024-12-01 | 2025-01-17 | 2025-01-24
Works | Overhaul of the fire system | Overhaul of the fire system | 1227096 | 1227096 | ODB | 2024-10-09 | 2024-10-14 | 2024-10-18 | 2024-10-21 | 2024-11-08 | 2024-11-27 | 2024-12-05 | 2024-12-11 | 2024-12-13 | 2024-12-17 | 2025-01-17 | 2025-01-24 | 2024-02-03 | 2024-02-28 | 2025-03-07
|  | TOTAL | 10987114 | 14347114

## DICT (hidden)
Procuring Department
[5 empty] | 7 | 14 | 14 | 7 | 1 | 21 | 14 | 7 | 14 | 7 | 10 | 14 | 42
DISCIPLINE | Project Description | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Supplies | IT Laptops | 60000 | 60000 | RFQ | 2024-04-26 | 2024-05-10 | 2024-05-24 | 2024-05-31 | 2024-06-01 | 2024-06-22 | 2024-07-06 | 2024-07-13 | 2024-07-27 | 2024-08-03 | 2024-08-13 | 2024-08-27 | 2024-10-08 | 2024-11-07 | 2024-11-14
| Users Laptops | 960000 | 960000 | ITT | 2024-04-26 | 2024-05-10 | 2024-05-24 | 2024-05-31 | 2024-06-01 | 2024-06-22 | 2024-07-06 | 2024-07-13 | 2024-07-27 | 2024-08-03 | 2024-08-13 | 2024-08-27 | 2024-10-08 | 2024-11-07 | 2024-11-14
| Tablets | 75000 | 75000 | RFQ | 2024-04-19 | 2024-05-03 | 2024-05-17 | 2024-05-24 | 2024-05-25 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-20 | 2024-07-27 | 2024-08-06 | 2024-08-20 | 2024-10-01 | 2024-10-31 | 2024-11-07
| Board Tablets | 189000 | 189000 | RFQ | 2024-04-19 | 2024-05-03 | 2024-05-17 | 2024-05-24 | 2024-05-25 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-20 | 2024-07-27 | 2024-08-06 | 2024-08-20 | 2024-10-01 | 2024-10-31 | 2024-11-07
| Smart Boards | 320000 | 320000 | RFQ | 2024-04-19 | 2024-05-03 | 2024-05-17 | 2024-05-24 | 2024-05-25 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-20 | 2024-07-27 | 2024-08-06 | 2024-08-20 | 2024-10-01 | 2024-10-31 | 2024-11-07
| Printers | 240000 | 240000 | RFQ | 2024-04-26 | 2024-05-10 | 2024-05-24 | 2024-05-31 | 2024-06-01 | 2024-06-22 | 2024-07-06 | 2024-07-13 | 2024-07-27 | 2024-08-03 | 2024-08-13 | 2024-08-27 | 2024-10-08 | 2024-11-07 | 2024-11-14
| Call Center Hardware and Licenses | 1000000 | 1000000 | ITT | 2024-04-26 | 2024-05-10 | 2024-05-24 | 2024-05-31 | 2024-06-01 | 2024-06-22 | 2024-07-06 | 2024-07-13 | 2024-07-27 | 2024-08-03 | 2024-08-13 | 2024-08-27 | 2024-10-08 | 2024-11-07 | 2024-11-14
| eHRDF Hardware | 2200000 | 2200000 | ITT | 2024-05-20 | 2024-06-03 | 2024-06-17 | 2024-06-24 | 2024-06-25 | 2024-07-16 | 2024-07-30 | 2024-08-06 | 2024-08-20 | 2024-08-27 | 2024-09-06 | 2024-09-20 | 2024-11-01 | 2024-12-01 | 2024-12-08
| Additional Wireless Access Points | 270000 | 270000 | RFQ | 2024-05-20 | 2024-06-03 | 2024-06-17 | 2024-06-24 | 2024-06-25 | 2024-07-16 | 2024-07-30 | 2024-08-06 | 2024-08-20 | 2024-08-27 | 2024-09-06 | 2024-09-20 | 2024-11-01 | 2024-12-01 | 2024-12-08
| Load Balancer and proxy server | 300000 | 300000 | RFQ | 2024-04-19 | 2024-05-03 | 2024-05-17 | 2024-05-24 | 2024-05-25 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-20 | 2024-07-27 | 2024-08-06 | 2024-08-20 | 2024-10-01 | 2024-10-31 | 2024-11-07
| Video Conferencing Hardware | 500000 | 500000 | ITT | 2024-05-20 | 2024-06-03 | 2024-06-17 | 2024-06-24 | 2024-06-25 | 2024-07-16 | 2024-07-30 | 2024-08-06 | 2024-08-20 | 2024-08-27 | 2024-09-06 | 2024-09-20 | 2024-11-01 | 2024-12-01 | 2024-12-08
| CCTV | 150000 | 150000 | RFQ | 2024-05-27 | 2024-06-10 | 2024-06-24 | 2024-07-01 | 2024-07-02 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-27 | 2024-09-03 | 2024-09-13 | 2024-09-27 | 2024-11-08 | 2024-12-08 | 2024-12-15
| IT accessories (ergonomic etc) | 300000 | 300000 | RFQ | 2024-05-20 | 2024-06-03 | 2024-06-17 | 2024-06-24 | 2024-06-25 | 2024-07-16 | 2024-07-30 | 2024-08-06 | 2024-08-20 | 2024-08-27 | 2024-09-06 | 2024-09-20 | 2024-11-01 | 2024-12-01 | 2024-12-08
Services | HRDC/BHRDS Website Enhancement | 100000 | 100000 | RFQ | 2024-07-01 | 2024-07-15 | 2024-07-29 | 2024-08-05 | 2024-08-06 | 2024-08-27 | 2024-09-10 | 2024-09-17 | 2024-10-01 | 2024-10-08 | 2024-10-18 | 2024-11-01 | 2024-12-13 | 2025-01-12 | 2025-01-19
| eHRDF Development | 6500000 | 6500000 | ITT | 2024-07-14 | 2024-07-14 | 2024-07-28 | 2024-08-04 | 2024-08-05 | 2024-08-26 | 2024-09-09 | 2024-09-16 | 2024-09-30 | 2024-10-07 | 2024-10-17 | 2024-10-31 | 2024-12-12 | 2025-01-11 | 2025-01-18
| eHRDF QA | 2500000 | 2500000 | ITT | 2024-07-15 | 2024-07-15 | 2024-07-29 | 2024-08-05 | 2024-08-06 | 2024-08-27 | 2024-09-10 | 2024-09-17 | 2024-10-01 | 2024-10-08 | 2024-10-18 | 2024-11-01 | 2024-12-13 | 2025-01-12 | 2025-01-19
| NCBSC and consultants Database | 300000 | 300000 | RFQ | 2024-04-01 | 2024-04-15 | 2024-04-29 | 2024-05-06 | 2024-05-07 | 2024-05-28 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-09 | 2024-07-19 | 2024-08-02 | 2024-09-13 | 2024-10-13 | 2024-10-20
| NCBSC SOUR (update eHRDF SOUR) | 200000 | 200000 | RFQ | 2024-04-01 | 2024-04-15 | 2024-04-29 | 2024-05-06 | 2024-05-07 | 2024-05-28 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-09 | 2024-07-19 | 2024-08-02 | 2024-09-13 | 2024-10-13 | 2024-10-20
| Multifactor Authentication Solution | 200000 | 200000 | RFQ | 2024-05-20 | 2024-06-03 | 2024-06-17 | 2024-06-24 | 2024-06-25 | 2024-07-16 | 2024-07-30 | 2024-08-06 | 2024-08-20 | 2024-08-27 | 2024-09-06 | 2024-09-20 | 2024-11-01 | 2024-12-01 | 2024-12-08
| Email security solution | 300000 | 300000 | RFQ | 2024-06-03 | 2024-06-17 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-30 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-09-20 | 2024-10-04 | 2024-11-15 | 2024-12-15 | 2024-12-22
| BPM Solution | 262000 | 262000 | RFQ | 2024-04-01 | 2024-04-15 | 2024-04-29 | 2024-05-06 | 2024-05-07 | 2024-05-28 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-09 | 2024-07-19 | 2024-08-02 | 2024-09-13 | 2024-10-13 | 2024-10-20
| SIEM | 380000 | 380000 | RFQ | 2024-06-03 | 2024-06-17 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-30 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-09-20 | 2024-10-04 | 2024-11-15 | 2024-12-15 | 2024-12-22
| LMO Website | 65000 | 65000 | RFQ | 2024-03-15 | 2024-03-29 | 2024-04-12 | 2024-04-19 | 2024-04-20 | 2024-05-11 | 2024-05-25 | 2024-06-01 | 2024-06-15 | 2024-06-22 | 2024-07-02 | 2024-07-16 | 2024-08-27 | 2024-09-26 | 2024-10-03
| HRDF system | 160000 | 160000 | RFQ | 2024-04-01 | 2024-04-15 | 2024-04-29 | 2024-05-06 | 2024-05-07 | 2024-05-28 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-09 | 2024-07-19 | 2024-08-02 | 2024-09-13 | 2024-10-13 | 2024-10-20
| UPS Batteries and firmware updates | 50000 | 50000 | RFQ | 2024-06-03 | 2024-06-17 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-30 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-09-20 | 2024-10-04 | 2024-11-15 | 2024-12-15 | 2024-12-22
| HR System | 100000 | 100000 | RFQ | 2024-07-01 | 2024-07-15 | 2024-07-29 | 2024-08-05 | 2024-08-06 | 2024-08-27 | 2024-09-10 | 2024-09-17 | 2024-10-01 | 2024-10-08 | 2024-10-18 | 2024-11-01 | 2024-12-13 | 2025-01-12 | 2025-01-19
| BPM (Budgeting) | 150000 | 150000 | RFQ | 2025-01-01 | 2025-01-15 | 2025-01-29 | 2025-02-05 | 2025-02-06 | 2025-02-27 | 2025-03-13 | 2025-03-20 | 2025-04-03 | 2025-04-10 | 2025-04-20 | 2025-05-04 | 2025-06-15 | 2025-07-15 | 2025-07-22
| ACCPAC support | 110000 | 110000 | RFQ | 2024-04-01 | 2024-04-15 | 2024-04-29 | 2024-05-06 | 2024-05-07 | 2024-05-28 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-09 | 2024-07-19 | 2024-08-02 | 2024-09-13 | 2024-10-13 | 2024-10-20
| Access Control Support | 120000 | 120000 | RFQ | 2024-06-03 | 2024-06-17 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-30 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-09-20 | 2024-10-04 | 2024-11-15 | 2024-12-15 | 2024-12-22
| MS Software licenses (M365, project Online P2, visio Online P2) | 1400000 | 1400000 | ITT | 2024-05-27 | 2024-06-10 | 2024-06-24 | 2024-07-01 | 2024-07-02 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-27 | 2024-09-03 | 2024-09-13 | 2024-09-27 | 2024-11-08 | 2024-12-08 | 2024-12-15
| Microsoft Software Assurance | 500000 | 500000 | ITT | 2024-06-17 | 2024-07-01 | 2024-07-15 | 2024-07-22 | 2024-07-23 | 2024-08-13 | 2024-08-27 | 2024-09-03 | 2024-09-17 | 2024-09-24 | 2024-10-04 | 2024-10-18 | 2024-11-29 | 2024-12-29 | 2025-01-05
| Firewall(fortigate & fortimail) | 250000 | 250000 | RFQ | 2024-05-06 | 2024-05-20 | 2024-06-03 | 2024-06-10 | 2024-06-11 | 2024-07-02 | 2024-07-16 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-23 | 2024-09-06 | 2024-10-18 | 2024-11-17 | 2024-11-24
| RUCKUS Wireless | 70000 | 70000 | RFQ | 2024-11-15 | 2024-11-29 | 2024-12-13 | 2024-12-20 | 2024-12-21 | 2025-01-11 | 2025-01-25 | 2025-02-01 | 2025-02-15 | 2025-02-22 | 2025-03-04 | 2025-03-18 | 2025-04-29 | 2025-05-29 | 2025-06-05
| ACCPAC | 130000 | 130000 | RFQ | 2024-06-01 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-07 | 2024-07-28 | 2024-08-11 | 2024-08-18 | 2024-09-01 | 2024-09-08 | 2024-09-18 | 2024-10-02 | 2024-11-13 | 2024-12-13 | 2024-12-20
| VIP- Sage (HR Module) + (Payroll & ESS) | 120000 | 120000 | RFQ | 2024-12-01 | 2024-12-15 | 2024-12-29 | 2025-01-05 | 2025-01-06 | 2025-01-27 | 2025-02-10 | 2025-02-17 | 2025-03-03 | 2025-03-10 | 2025-03-20 | 2025-04-03 | 2025-05-15 | 2025-06-14 | 2025-06-21
| CODETWO Mail Signature | 6000 | 6000 | RFQ | 2024-07-05 | 2024-07-19 | 2024-08-02 | 2024-08-09 | 2024-08-10 | 2024-08-31 | 2024-09-14 | 2024-09-21 | 2024-10-05 | 2024-10-12 | 2024-10-22 | 2024-11-05 | 2024-12-17 | 2025-01-16 | 2025-01-23
| ProQuest database | 48000 | 48000 | RFQ | 2024-11-01 | 2024-11-15 | 2024-11-29 | 2024-12-06 | 2024-12-07 | 2024-12-28 | 2025-01-11 | 2025-01-18 | 2025-02-01 | 2025-02-08 | 2025-02-18 | 2025-03-04 | 2025-04-15 | 2025-05-15 | 2025-05-22
| Webroot Subscription | 80000 | 80000 | RFQ | 2024-07-05 | 2024-07-19 | 2024-08-02 | 2024-08-09 | 2024-08-10 | 2024-08-31 | 2024-09-14 | 2024-09-21 | 2024-10-05 | 2024-10-12 | 2024-10-22 | 2024-11-05 | 2024-12-17 | 2025-01-16 | 2025-01-23
| SYSAID ITSM Helpdesk | 95000 | 95000 | RFQ | 2024-11-15 | 2024-11-29 | 2024-12-13 | 2024-12-20 | 2024-12-21 | 2025-01-11 | 2025-01-25 | 2025-02-01 | 2025-02-15 | 2025-02-22 | 2025-03-04 | 2025-03-18 | 2025-04-29 | 2025-05-29 | 2025-06-05
| BOFINET DR Site Rental | 90000 | 90000 | RFQ | 2024-05-27 | 2024-06-10 | 2024-06-24 | 2024-07-01 | 2024-07-02 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-27 | 2024-09-03 | 2024-09-13 | 2024-09-27 | 2024-11-08 | 2024-12-08 | 2024-12-15
| Bitrix24 | 60000 | 60000 | RFQ | 2024-09-01 | 2024-09-15 | 2024-09-29 | 2024-10-06 | 2024-10-07 | 2024-10-28 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2024-12-09 | 2024-12-19 | 2025-01-02 | 2025-02-13 | 2025-03-15 | 2025-03-22
| SSL Certificates | 20000 | 20000 | RFQ | 2024-06-03 | 2024-06-17 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-30 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-09-20 | 2024-10-04 | 2024-11-15 | 2024-12-15 | 2024-12-22
| Cisco Smartnet | 160000 | 160000 | RFQ | 2024-06-03 | 2024-06-17 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-30 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-09-20 | 2024-10-04 | 2024-11-15 | 2024-12-15 | 2024-12-22
| Veeam | 170000 | 170000 | RFQ | 2024-08-01 | 2024-08-15 | 2024-08-29 | 2024-09-05 | 2024-09-06 | 2024-09-27 | 2024-10-11 | 2024-10-18 | 2024-11-01 | 2024-11-08 | 2024-11-18 | 2024-12-02 | 2025-01-13 | 2025-02-12 | 2025-02-19
| VMWARE - Main Site | 170000 | 170000 | RFQ | 2024-08-01 | 2024-08-15 | 2024-08-29 | 2024-09-05 | 2024-09-06 | 2024-09-27 | 2024-10-11 | 2024-10-18 | 2024-11-01 | 2024-11-08 | 2024-11-18 | 2024-12-02 | 2025-01-13 | 2025-02-12 | 2025-02-19
| VMWARE - DR Site | 170000 | 170000 | RFQ | 2024-08-01 | 2024-08-15 | 2024-08-29 | 2024-09-05 | 2024-09-06 | 2024-09-27 | 2024-10-11 | 2024-10-18 | 2024-11-01 | 2024-11-08 | 2024-11-18 | 2024-12-02 | 2025-01-13 | 2025-02-12 | 2025-02-19
| NESSUS | 95000 | 95000 | RFQ | 2024-04-19 | 2024-05-03 | 2024-05-17 | 2024-05-24 | 2024-05-25 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-20 | 2024-07-27 | 2024-08-06 | 2024-08-20 | 2024-10-01 | 2024-10-31 | 2024-11-07
| Secondary Antirus (Symantec) | 30000 | 30000 | RFQ | 2024-11-15 | 2024-11-29 | 2024-12-13 | 2024-12-20 | 2024-12-21 | 2025-01-11 | 2025-01-25 | 2025-02-01 | 2025-02-15 | 2025-02-22 | 2025-03-04 | 2025-03-18 | 2025-04-29 | 2025-05-29 | 2025-06-05
| E-Signature Solution | 100000 | 100000 | RFQ | 2024-11-15 | 2024-11-29 | 2024-12-13 | 2024-12-20 | 2024-12-21 | 2025-01-11 | 2025-01-25 | 2025-02-01 | 2025-02-15 | 2025-02-22 | 2025-03-04 | 2025-03-18 | 2025-04-29 | 2025-05-29 | 2025-06-05
| Adobe Creative Suite | 25000 | 25000 | RFQ | 2024-04-19 | 2024-05-03 | 2024-05-17 | 2024-05-24 | 2024-05-25 | 2024-06-15 | 2024-06-29 | 2024-07-06 | 2024-07-20 | 2024-07-27 | 2024-08-06 | 2024-08-20 | 2024-10-01 | 2024-10-31 | 2024-11-07
| Printing Solution | 90000 | 90000 | RFQ | 2024-08-01 | 2024-08-15 | 2024-08-29 | 2024-09-05 | 2024-09-06 | 2024-09-27 | 2024-10-11 | 2024-10-18 | 2024-11-01 | 2024-11-08 | 2024-11-18 | 2024-12-02 | 2025-01-13 | 2025-02-12 | 2025-02-19
| Strategy management tool | 140000 | 140000 | RFQ | 2024-05-01 | 2024-05-15 | 2024-05-29 | 2024-06-05 | 2024-06-06 | 2024-06-27 | 2024-07-11 | 2024-07-18 | 2024-08-01 | 2024-08-08 | 2024-08-18 | 2024-09-01 | 2024-10-13 | 2024-11-12 | 2024-11-19
| BPM (Budgeting) | 85000 | 85000 | RFQ | 2025-01-01 | 2025-01-15 | 2025-01-29 | 2025-02-05 | 2025-02-06 | 2025-02-27 | 2025-03-13 | 2025-03-20 | 2025-04-03 | 2025-04-10 | 2025-04-20 | 2025-05-04 | 2025-06-15 | 2025-07-15 | 2025-07-22
| SPSS | 1500000 | 1500000 | ITT | 2024-10-02 | 2024-10-16 | 2024-10-30 | 2024-11-06 | 2024-11-07 | 2024-11-28 | 2024-12-12 | 2024-12-19 | 2025-01-02 | 2025-01-09 | 2025-01-19 | 2025-02-02 | 2025-03-16 | 2025-04-15 | 2025-04-22
| Oracle Licenses | 250000 | 250000 | RFQ | 2024-05-01 | 2024-05-15 | 2024-05-29 | 2024-06-05 | 2024-06-06 | 2024-06-27 | 2024-07-11 | 2024-07-18 | 2024-08-01 | 2024-08-08 | 2024-08-18 | 2024-09-01 | 2024-10-13 | 2024-11-12 | 2024-11-19
| LAN Maintenace and Support | 250000 | 250000 | RFQ | 2024-05-01 | 2024-05-15 | 2024-05-29 | 2024-06-05 | 2024-06-06 | 2024-06-27 | 2024-07-11 | 2024-07-18 | 2024-08-01 | 2024-08-08 | 2024-08-18 | 2024-09-01 | 2024-10-13 | 2024-11-12 | 2024-11-19
| WIFI Maintenace and Support |  |  | RFQ | 2024-05-01 | 2024-05-15 | 2024-05-29 | 2024-06-05 | 2024-06-06 | 2024-06-27 | 2024-07-11 | 2024-07-18 | 2024-08-01 | 2024-08-08 | 2024-08-18 | 2024-09-01 | 2024-10-13 | 2024-11-12 | 2024-11-19
| Laptops Maintence and Support |  |  | RFQ | 2024-05-06 | 2024-05-20 | 2024-06-03 | 2024-06-10 | 2024-06-11 | 2024-07-02 | 2024-07-16 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-23 | 2024-09-06 | 2024-10-18 | 2024-11-17 | 2024-11-24
| Printers Maintenance and Support |  |  | RFQ | 2024-05-06 | 2024-05-20 | 2024-06-03 | 2024-06-10 | 2024-06-11 | 2024-07-02 | 2024-07-16 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-23 | 2024-09-06 | 2024-10-18 | 2024-11-17 | 2024-11-24
| Server Hardware Support and Maintenance |  |  | RFQ | 2024-05-06 | 2024-05-20 | 2024-06-03 | 2024-06-10 | 2024-06-11 | 2024-07-02 | 2024-07-16 | 2024-07-23 | 2024-08-06 | 2024-08-13 | 2024-08-23 | 2024-09-06 | 2024-10-18 | 2024-11-17 | 2024-11-24
| Server Software Support and Maintenance |  |  | RFQ | 2024-05-05 | 2024-05-19 | 2024-06-02 | 2024-06-09 | 2024-06-10 | 2024-07-01 | 2024-07-15 | 2024-07-22 | 2024-08-05 | 2024-08-12 | 2024-08-22 | 2024-09-05 | 2024-10-17 | 2024-11-16 | 2024-11-23
| Endpoint Visibility and Control |  |  | RFQ | 2024-11-06 | 2024-11-20 | 2024-12-04 | 2024-12-11 | 2024-12-12 | 2025-01-02 | 2025-01-16 | 2025-01-23 | 2025-02-06 | 2025-02-13 | 2025-02-23 | 2025-03-09 | 2025-04-20 | 2025-05-20 | 2025-05-27
| Smartboards support and maintenance |  |  | RFQ | 2024-05-07 | 2024-05-21 | 2024-06-04 | 2024-06-11 | 2024-06-12 | 2024-07-03 | 2024-07-17 | 2024-07-24 | 2024-08-07 | 2024-08-14 | 2024-08-24 | 2024-09-07 | 2024-10-19 | 2024-11-18 | 2024-11-25
| Backups Support and Maintenance |  |  | RFQ | 2024-05-08 | 2024-05-22 | 2024-06-05 | 2024-06-12 | 2024-06-13 | 2024-07-04 | 2024-07-18 | 2024-07-25 | 2024-08-08 | 2024-08-15 | 2024-08-25 | 2024-09-08 | 2024-10-20 | 2024-11-19 | 2024-11-26
| TOTAL | 24165000 | 24165000
Total |  | 48330000 | 48330000
eRecords
Business Continuity Contigency
Develop and implement HRDC ICT Governance Risk Management Framework (Governance Risk & Compliance SOUR)
CURA Risk Management Software
eHRDF Workhshops |  | 800000 | 800000 | RFQ
Formulas:
Closing date for tenders = [Issuing of invitation to tender]+1
Submission of Evaluation Report to POU = [Verification of Evaluation Report by PU]+7
Pre-Adjudication by POU = [Submission of Evaluation Report to POU]+14
Award Decision by AO = [Pre-Adjudication by POU]+7
Cooling Off and Debriefing = [Award Decision by AO]+10
Contract Signing = [Cooling Off and Debriefing]+14
Commencement of Project Implementation = [Contract Signing]+42
Completion of project Implementaion = [Commencement of Project Implementation]+30
End of Activity Report = [Completion of project Implementaion]+7

## DHRP-DD (hidden)
DISCIPLINE | Project Name | Project Description | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender/RFQ | Closing date for tenders/RFQ | Evaluation of tender/RFQ by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO/map | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | Conduct a Comprehensive Survey of Skills in Demand | Development of data collection tools | 50000 | 50000 | Micro Procurement | N/A | N/A | N/A | 2024-05-13 | 2024-05-14 | N/A | N/A | N/A | N/A | 2024-05-15 | N/A | N/A | 2024-05-31 | 2024-06-30 | 2024-07-09
|  | Data Collection for 17 sectors | 800000 | 800000 | Micro Procurement | N/A | N/A | N/A | 2024-07-09 | 2024-07-10 | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | 2024-07-31 | 2024-12-31 | 2024-01-09
|  | Stakeholder Validations Workshops (Travel, Venue, Meals) | 400000 | 400000 | Micro Procurement | N/A | N/A | N/A | 2025-01-06 | 2025-01-07 | N/A | N/A | N/A | N/A | 2025-01-08 | N/A | N/A | 2025-01-14 | 2025-03-31 | 2025-04-09
| Promote Implementation Sector HRD Plans | Continuation of the Skills Transfer Project ( Travel, Venue, Meals) | 75000 | 75000 | Micro Procurement | N/A | N/A | N/A | 2024-04-10 | 2024-04-11 | N/A | N/A | N/A | N/A | 2024-04-12 | N/A | N/A | 2024-04-15 | 2025-03-31 | 2025-04-09
|  | Capacity Development Workshops on Solutions to Skills Development Issues( Travel, venue, Meals) | 65000 | 65000 | Micro Procurement | N/A | N/A | N/A | 2024-05-14 | 2024-05-15 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | 2024-05-31 | 2024-09-30 | 2024-10-10
|  | International Conference and Workshops ( Travel, Venue, Meals) | 60000 | 60000 | Micro Procurement | N/A | N/A | N/A | 2024-05-21 | 2024-05-22 | N/A | N/A | N/A | N/A | 2024-05-23 | N/A | N/A | 2024-05-31 | 2025-03-31 | 2025-04-09
| Provide for policy advice in all matters of Human Resource Development | Capacity Building Workshops by (BIDPA) (Travel, Venue, Meals) | 100000 | 100000 | Micro Procurement | N/A | N/A | N/A | 2024-05-21 | 2024-05-22 | N/A | N/A | N/A | N/A | 2024-05-23 | N/A | N/A | 2024-05-31 | 2024-06-30 | 2024-07-10
|  | Travel & Registration fees for conferences | 100000 | 100000 | Micro Procurement | N/A | N/A | N/A | 2024-05-21 | 2024-05-22 | N/A | N/A | N/A | N/A | 2024-05-23 | N/A | N/A | 2024-05-31 | 2025-03-31 | 2025-04-09
|  | Stakeholder Engagements For Development of Policy Papers ( Travel, Venue, Meals) | 50000 | 50000 | Micro Procurement | N/A | N/A | N/A | 2024-07-09 | 2024-07-10 | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | 2024-07-31 | 2025-03-31 | 2025-04-09
|  | Dissemination of Monitoring Reports and Policy Papers (Travel, Venue, Meals) | 110000 | 110000 | Micro Procurement | N/A | N/A | N/A | 2025-01-13 | 2025-01-14 | N/A | N/A | N/A | N/A | 2025-01-15 | N/A | N/A | 2025-01-31 | 2025-03-31 | 2025-04-09
| Sector Committee Meetings | Sector Committee Workshops( Travel, Venue, meals) | 120000 | 120000 | Micro Procurement | N/A | N/A | N/A | 2024-07-09 | 2024-07-10 | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | 2024-07-31 | 2025-03-31 | 2025-04-09
Total |  |  | 605000 | 605000

## RISK (hidden)
DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | Enterprise Risk Management training for the Board and Executive- Inhouse Training | Enterprise Risk Management training for the Board and Executive (Conference facilities, accomodation, Refreshments) | 300000 | 300000 | Micro Procurement | 2024-04-22 | N/A | N/A | 2024-04-24 | 2024-04-26 | 2024-04-29 | N/A | N/A | N/A | 2024-04-29 | N/A | N/A | 2024-05-03 | 2024-09-27 | 2024-10-11 |  | 2024-05-03
Services | Conduct and Culture Risk Training - Inhouse | Conduct and Culture Risk Training - Inhouse- (Conference facilities, Refreshments) | 100000 | 100000 | Micro Procurement | 2024-04-22 | N/A | N/A | 2024-04-24 | 2024-04-26 | 2024-04-29 | N/A | N/A | N/A | 2024-04-29 | N/A | N/A | 2024-05-03 | 2024-09-27 | 2024-10-11
Services | Sustainability and Climate Risk Training for Executive Management and Board | Sustanability and Climate Risk Inhouse Training- Conference facilities, refreshments) | 200000 | 200000 | Miro Procurement | 2024-08-01 | N/A | N/A | 2024-08-05 | 2024-08-07 | 2024-08-09 | N/A | N/A | N/A | 2024-08-13 | N/A | N/A | 2024-08-26 | 2024-08-28 | 2024-09-06
| Business Continuity Management Roll oute | Business Continuity Mnagement Roll Out- Inhouse Training - Conference facility, refreshments) | 100000 | 100000 | Micro Procurement | 2024-10-21 | N/A | N/A | 2024-10-23 | 2024-10-25 | 2024-10-29 | N/A | N/A | N/A | 2024-10-31 | N/A | N/A | 2024-10-11 | 2024-10-14 | 2024-10-21 | 2024-06-15 | 2024-07-15 | 2024-07-31
Total |  |  | 700000 | 700000

## IA (hidden)
Procuring Department
DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | Assurance of ERM Processes | Assurance of ERM Processes | 100 000.00 | 100 000.00 | Micro Procurement | 2024-09-09 | 2024-09-20 | N/A | 2024-09-24 | 2024-10-11 | 2024-10-14 | 2024-10-18 | 2024-10-22 | 2024-10-25 | 2024-10-29 | 2024-11-12 | 2024-12-13 | 2025-01-13 | 2025-02-28 | 2025-03-07
Services | Internal Audit Quality Review | Internal Audit Quality Review | 500 000.00 | 500 000.00 | Quoutation Proposal | 2024-07-14 | 2024-07-18 | N/A | 2024-07-22 | 2024-08-02 | 2024-08-12 | 2024-09-20 | 2024-09-22 | 2024-10-07 | 2024-10-11 | 2024-10-25 | 2024-11-15 | 2024-11-25 | 2024-12-13 | 2025-01-10
Total |  |  | 600 000 | 600 000

## Strategy (hidden)
Procuring Department: Strategy Office
DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | HRDC Mandate Dissemination | HRDC Dissemination(Travel, Venue and Meals) | 150000 | 150000 | Quoutation Proposal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2025-03-20 | 2025-03-31
Services | Strategy/Business Plan Cascading | Business Plan Cascading ( Venue, Meals, travel) | 100000 | 100000 | Micro-procurement | 2024-04-19 | N/A | N/A | 2024-04-23 | 2024-04-26 | 2024-04-27 | N/A | N/A | N/A | 2024-04-29 | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-05-10
Services | NHRD Conference | Conference Facility and other services | 1000000 | 1000000 | Quoutation Proposal/Micro Procurement | 2024-06-17 | 2024-04-23 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Services | 2024-2025 Business Plan Mid-term Review | Business Plan Mid Term Review( Venue, Meals, Travel) | 100000 | 100000 | Micro Procurement | 2024-09-16 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-24 | 2024-09-26 | 2024-09-27 | 2024-10-02 | 2024-10-04 | 2024-10-07 | N/A | N/A | 2024-10-14 | 2024-10-15 | 2024-10-25
Services | 2025-2026 Business Plan Development | 2025-2026- Business Plan zdevelopment ( Venue, Meals, travel) | 300000 | 300000 | Micro Procurement | 2025-01-03 | 2025-01-06 | 2025-01-08 | 2025-01-10 | 2025-01-14 | 2025-01-16 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | N/A | N/A | 2025-01-27 | 2025-01-29 | 2025-02-07
|  | TOTAL | 1650000 | 1650000

## DSRDI (hidden)
No | DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
1 | Services | Publicity for LMO Press Briefings | Adverts | 16500 | 16500 | Micro Procurement | 2024-06-03 | N/A | N/A | 2024-06-21 | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-30 | 2024-07-10
2 | Services | Stakeholder consultations and press briefs | Stakeholder consultations and press briefs ( Venue, Refreshment, Travel) | 24750 | 24750 | Micro Procurement | 2024-06-07 | N/A | N/A | 2024-06-12 | 2024-06-17 | 19/06/2024N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | 2024-06-22 | 2024-06-30 | 2024-07-11
3 | Services | Printing and Stationery for LMO activities | Stationery for LMO Activities | 16500 | 16500 | Micro Procurement | 2024-06-03 | N/A | N/A | 2024-06-07 | 2024-06-12 | 2024-06-17 | N/A | N/A | N/A | 2024-06-19 | N/A | N/A | 2024-06-21 | 2024-06-30 | 2024-07-12
4 | Services | Labour Market Intelligence activites | Labour Market Intelligence activites- (call for papers, conference facilities) | 99000 | 99000 | Micro Procurement | 2024-08-05 | N/A | N/A | 2024-08-09 | 2024-08-16 | 2024-08-21 | N/A | N/A | N/A | 2024-09-09 | N/A | N/A | 2024-09-16 | 2024-09-20 | 2024-07-13
5 | Services | LMO benchmarking activities | LMO Benchmarking ( Travel, Accomodation, Meals) | 125000 | 125000 | Micro Procurement | 2024-06-03 | N/A | N/A | 2024-06-07 | 2024-06-12 | 2024-06-14 | N/A | N/A | N/A | 2024-06-18 | N/A | N/A | 2024-06-21 | 2024-06-21 | 2024-07-14
6 | Services | LMO Committee meetings | LMO Committee Meetings (Venue, Travel, Accomodation,Refreshments | 75000 | 75000 | Micro Procurement | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2025-03-31 | 2025-04-09
7 | Services | Meetings for SLAs for LMIS portal content | SLAs Meetings for LMIS Portal Content ( workshop facility) | 40000 | 40000 | Micro Procurement | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2025-03-31 | 2025-04-09
8 | Services | Implementation of SLAs for LMIS portal content | Implementation of SLAs for LMIS portal content | 400000 | 400000 | Direct Procurement | 2024-04-01 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-05-17 | 2024-05-24 | 2024-05-31 | 2024-06-03 | 2024-06-07 | 2024-06-07 | 2024-06-14 | 2024-06-21 | 2024-07-01 | 2025-03-31 | 2025-04-09
9 | Services | Pre-launch LMIS Portal UAT | Pre Launch LMIS Portal UAT( travel, accomodation, meals) | 200000 | 200000 | Quoutation Proposal | 2024-04-02 | N/A | N/A | 2025-03-31 | 2025-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-04-09
10 | Services | LMIS Brand Development Stakeholder Consultations | LMIS Brand Development Consultations ( Venue, Travel, Accomodation and Refreshments) | 80000 | 80000 | Quoutation Proposal | 2024-04-12 | N/A | N/A | 2024-06-30 | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-06-30 | 2024-07-19
11 | Services | LMIS Promotional Materials & Merchandise | LMIS Promotional Materials | 300000 | 300000 | Quoutation Proposal/ Micro procurement | 2024-06-01 | 2024-06-10 | 2024-06-24 | 2024-07-31 | 2024-07-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-07-31 | 2024-07-19
12 | Services | Implementation of the LMIS Change Management Communication Plan | LMIS Change Management Plan ( advertisement, worskhop facility) | 300000 | 300000 | Micro Procurement | 2024-04-02 | N/A | N/A | 2025-03-31 | 2025-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2025-03-31 | 2025-04-10
13 | Services | Post launch LMIS UAT activities | Post Paunch LMIS UAT activities ( travel, venue, meals) | 250000 | 250000 | Micro Procurement | 2024-10-01 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2025-03-31 | 2025-04-09
14 | Services | Capacity building/ training for National Skills Audit activities | Capacity building/ training for National Skills Audit activities( Facilitator, Venue, Meals, Accomodation) | 450000 | 450000 | Micro Procurement | 2024-10-02 | N/A | N/A | 2025-03-31 | 2025-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2025-03-31 | 2025-04-10
15 | Services | Professional services for undertaking of the National Skills Audit | Professional services for undertaking of the National Skills Audit | 1300000 | 1300000 | ODB | 2024-04-01 | 2024-04-19 | 2024-04-22 | 2024-04-26 | 2024-05-17 | 2024-05-24 | 2024-05-31 | 2024-06-03 | 2024-06-07 | 2024-06-07 | 2024-06-14 | 2024-06-21 | 2024-07-01 | 2025-03-31 | 2025-04-10
16 | Services | National Skills Audit stakeholder meetings | National Skills Audit Stakeholder Meetings ( Travel, Accomodation, Meals) | 200000 | 200000 | Micro Procurement | 2024-04-02 | N/A | N/A | N/A | 2025-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2025-03-31 | 2025-04-10
17 | Services | National Skills Audit Project Printing and Stationery | Stationery for National Skills Audit | 50000 | 50000 | Mcro Procurement | 2025-02-01 | N/A | N/A | N/A | 2025-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-01 | 2025-03-31 | 2025-04-10
18 | Services | Newspapers and magazines | Newspapers and Magazines | 120000 | 120000 | Quoutation Proposal | 2024-04-02 | N/A | N/A | N/A | 2025-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2025-03-31 | 2025-04-10
19 | Services | Capacity Building of Central Government on the new Job Matching platform | Capacity building/ training for National Skills Audit activities( Facilitator, Venue, Meals, Accomodation) | 132000 | 132000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-08-25 | 2024-08-22 | 2024-08-29 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-16 | N/A | N/A | 2024-09-23 | 2024-09-26 | 2024-10-11
20 | Services | Capacity Building of Local Government on the new Job Matching platform | Capacity building of Local Govenrment on the new Job Matching ( Travel, Accomodation, Meals, Venue) | 182000 | 182000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-08-25 | 2024-08-22 | 2024-08-29 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-16 | N/A | N/A | 2024-10-07 | 2024-10-11 | 2024-07-29
21 | Services | Capacity Building of SOEs on the New Job Matching Platform | Capacity Building of SOEs on the SOEs on the New Job matching Platform( Travel, Accomodation, Meals, Venue) | 100000 | 100000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-08-25 | 2024-08-22 | 2024-08-29 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-16 | N/A | N/A | 2024-10-14 | 2024-10-18 | 2024-10-26
22 | Services | Capacity Building of Business Botswana Member Organisations on the New Job Matching Platform | Capacity Building of Business Botswana and Member Organisation on the New Job Matching Platform ( Travel, Accomodation, Meals, Venue) | 250000 | 250000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-08-25 | 2024-08-22 | 2024-08-29 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-16 | N/A | N/A | 2024-10-21 | 2024-10-25 | 2024-11-04
23 | Services | Capacity Building of District Labour Offices on the new Job Matching platform | Capacity Building of District Labour Offices on the new Job Matching platform( Travel, Accomodation, Meals, Venue) | 132000 | 132000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-08-25 | 2024-08-22 | 2024-08-29 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-16 | N/A | N/A | 2024-10-28 | 2024-10-31 | 2024-11-12
24 | Services | Capacity building of Regional Education Officers on the new Job Matching platform | Capacity building of Regional Education Officers on the new Job Matching platform (Travel, Accomodation, Meals, Venue) | 132000 | 132000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-08-25 | 2024-08-22 | 2024-08-29 | 2024-09-04 | 2024-09-06 | 2024-09-11 | 2024-09-16 | N/A | N/A | 2024-11-04 | 2024-11-08 | 2024-11-19
25 | Services | Prepare & upload ETP information onto LMIS Portal | Prepare & upload ETP information onto LMIS Portal( Venue, meals) | 50000 | 50000 | Micro Procurement | 2024-07-02 | N/A | N/A | 2024-09-30 | 2024-09-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-15 | 2024-11-26
26 | Services | Prepare & upload subsector specific information onto LMIS Portal | Prepare & upload subsector specific information onto LMIS Portal ( venue, meals) | 200000 | 200000 | Quoutation Proposal | 2024-07-02 | N/A | N/A | 2024-09-30 | 2024-09-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-26 | 2024-12-10
27 | Services | Prepare & upload data on potential employers by sector/ subsector onto LMIS Portal | Prepare & upload data on potential employers by sector/ subsector onto LMIS Portal (Venue, meals) | 50000 | 50000 | Micro Procurement | 2024-07-02 | N/A | N/A | 2024-09-30 | 2024-09-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-28 | 2024-11-30 | 2024-12-06
28 | Services | Develop & upload video and other multi-media content onto LMIS Portal | Tender to Develop & upload video and other multi-media content onto LMIS Portal | 400000 | 400000 | QPP | 2024-04-01 | N/A | N/A | 2024-05-31 | 2024-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | 2024-06-12
29 | Services | Facilitate requirements validation for the Employment Information subsystem | Facilitate requirements validation for the Employment Information subsystem ( Travel, venue, meals) | 50000 | 50000 | Micro Procurement | 2024-04-01 | N/A | N/A | 2024-05-31 | 2024-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-06 | 2024-06-18
30 | Services | Facilitate Basic Education requirements validation for LMIS EIS | Facilitate Basic Education requirements validation for LMIS EIS (travel, venue, meals) | 100000 | 100000 | Micro Procurement | 2024-04-01 | N/A | N/A | 2024-05-31 | 2024-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-14 | 2024-06-24
31 | Services | Facilitate preparation & uploading of Basic Education data onto LMIS portal | Facilitate preparation & uploading of Basic Education data onto LMIS portal( travel, accomodation, meals)) | 50000 | 50000 | Micro Procurement | 2024-06-01 | N/A | N/A | 2024-08-31 | 2024-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-30 | 2024-09-10
32 | Services | Facilitate undertaking of employer survey | Facilitate undertaking of employer survey-(travel, accomodation, meals) | 400000 | 400000 | Direct Procurement | 2024-06-01 | N/A | N/A | 2024-08-31 | 2024-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-06 | 2024-10-11
33 | Services | Facilitate preparation & uploading of data for the Employment Information subsystem | Facilitate preparation & uploading of data for the Employment Information subsystem ( travel, accomodation,meals) | 50000 | 50000 | Micro Procurement | 2024-06-01 | N/A | N/A | 2024-08-31 | 2024-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-31 | 2024-09-10
34 | Services | Produce the 2023 Tertiary Education statistics report | Tertiary Education Statistics Report (report formating and printing) | 60000 | 60000 | Micro Procurement | 2024-08-01 | N/A | N/A | 2024-08-05 | 2024-08-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-10-01 | 2024-10-10
35 | Services | Produce the 2024 Education statistics report | Tertiary Education Statistics Report (report formating and printing) | 80000 | 80000 | Micro Procurement | 2025-02-03 | N/A | N/A | 2024-02-07 | 2024-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-31 | 2025-03-31
36 | Services | Conduct 2024/25 Census | Conduct Census ( Travel, accomodation, worskhop facility) | 200000 | 200000 | Micro Procurement | 2024-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2025-02-28 | 2025-03-31
|  |  | TOTAL | 6664750 | 6664750

## DF (hidden)
| DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
HRDF
70 | Services | Floating of adverts for closing date & fraud awareness | Adverts | 380000 | 380000 | Micro Procurement | 2024-04-15 | N/A | N/A | 2024-04-17 | 2024-04-18 | 2024-04-20 | N/A | N/A | N/A | 2024-04-22 | N/A | N/A | 2024-05-01 | 2024-06-30 | 2024-07-10
71 | Services | Claims collection and workplace support -Jwaneng | Claims collection and workplace support -Jwaneng ( travel, accomodation and meals) | 19250 | 19250 | Micro Procurement | 2024-04-02 | N/A | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | N/A | N/A | N/A | 2024-04-12 | N/A | N/A | 2023-04-15 | 2023-04-17 | 2024-04-22
72 | Services | Claims collection and workplace support -Maun | Claims collection and workplace support -Maun ( Travel, accomodation and meals) | 91000 | 91000 | Micro Procurement | 2024-04-02 | N/A | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | N/A | N/A | N/A | 2024-04-12 | N/A | N/A | 2024-04-15 | 2024-04-24 | 2024-05-03
73 | Services | Claims collection and workplace support -Francistown | Claims collection and workplace support -Francistown- (Travel, Accomodation and Meals) | 70500 | 70500 | Micro Procurement | 2024-04-02 | N/A | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | N/A | N/A | N/A | 2024-04-12 | N/A | N/A | 2024-04-28 | 2024-05-05 | 2024-05-12
74 | Services | Claims collection and workplace support- Palapye | Claims collection and workplace support- Palapye ( travel, accomodation and meals) | 69500 | 69500 | Micro Procurement | 2024-04-02 | N/A | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | N/A | N/A | N/A | 2024-04-12 | N/A | N/A | 2024-04-22 | 2024-05-01 | 2024-05-10
75 | Services | Capacity building-breakfast meeting in Maun | Capacity building-breakfast meeting in Maun- ( Conference facility, travel, accomodation) | 87188 | 87188 | Micro Procurement | 2024-07-02 | N/A | N/A | 2024-07-08 | 2024-07-10 | 2024-07-12 | N/A | N/A | N/A | 2024-07-22 | N/A | N/A | 2024-08-01 | 2024-11-01 | 2024-12-10
76 | Services | Capacity building-breakfast meeting in Francistown | Capacity building-breakfast meeting in Francistown ( Conference facility, travel, accomodation) | 87188 | 87188 | Micro Procurement | 2024-06-05 | N/A | N/A | 2024-06-07 | 2024-06-11 | 2024-06-13 | N/A | N/A | N/A | 2024-06-18 | N/A | N/A | 2024-07-01 | 2024-07-31 | 2024-08-10
77 | Services | Capacity building-breakfast show Kasane | Capacity building-breakfast show Kasane- Conference facility, travel, accomodation) | 71625 | 71625 | Micro Procurement | 2024-06-06 | N/A | N/A | 2024-05-08 | 2024-05-13 | 2024-05-16 | N/A | N/A | N/A | 2024-05-20 | N/A | N/A | 2024-06-01 | 2024-07-31 | 2024-12-31
78 | Services | HRDF Consultative meetings (GC) | HRDF Consultative meetings (GC)- Venue, refreshments | 60000 | 60000 | Micro Procurement | 2024-08-02 | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-08-12 | N/A | N/A | N/A | 2024-08-14 | N/A | N/A | 2024-09-01 | 2025-09-30 | 2024-08-07
79 | Services | HRDF Consultative meetings (FC) | HRDF Consultative meetings (GC)- Venue, refreshments, travel, accomodation | 37584 | 37584 | Micro Procurement | 2024-08-02 | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-08-12 | N/A | N/A | N/A | 2024-08-14 | N/A | N/A | 2024-09-01 | 2025-09-30 | 2025-09-03
80 | Services | HRDF Consultative meetings (Maun) | HRDF Consultative meetings (Maun)- Travel, accomodation, venue, meals) | 33617 | 33617 | Micro Procurement | 2024-08-02 | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-08-12 | N/A | N/A | N/A | 2024-08-14 | N/A | N/A | 2024-09-01 | 2025-09-30 | 2024-10-10
81 | Services | HRDF Consultative meetings (Palapye) | HRDF Consultative meetings (Maun)- Travel, accomodation, venue, meals) | 33417 | 33417 | Micro Procurement | 2024-08-02 | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-08-12 | N/A | N/A | N/A | 2024-08-14 | N/A | N/A | 2024-09-01 | 2025-09-30 | 2024-10-10
82 | Services | HRDF Consultative meetings (Ghanzi) | HRDF Consultative meetings (Ghanzi)Travel, accomodation, venue, meals) | 56854 | 56854 | Micro Procurement | 2024-08-02 | N/A | N/A | 2024-08-06 | 2024-08-08 | 2024-08-12 | N/A | N/A | N/A | 2024-08-14 | N/A | N/A | 2024-09-01 | 2025-09-30 | 2024-10-10
|  |  | Total HRDF Unit | 1097723 | 1097723 | [15 empty] | 2025-09-30
| e-HRDFS Project | [19 empty] | 2025-07-10
83 | Supplies | Design, Development and Implementation of e-HRDF | e-HRDF Hardware Procurement | 3000000 | 3000000 | ODB | 2024-05-31 | 2024-06-14 | 2024-06-28 | 2024-07-10 | 2024-07-12 | 2024-08-02 | 2024-08-16 | 2024-08-23 | 2024-08-30 | 2024-09-06 | 2024-09-24 | 2024-09-27 | 2024-10-01 | 2024-11-01 | 2025-07-10
84 | Supplies | Design, Development and Implementation of e-HRDF | e- HRDF Hardware (Laptops and Tablets) | 90000 | 90000 | Micro Procurement | 2024-05-27 | N/A | N/A | 2024-06-04 | 2024-06-10 | 2024-06-17 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | 2024-07-01 | 2025-06-27 | 2024-09-09
85 | Services | Consultancy Services for the Procurement of Quality Assurance Services for the eHRDFS. | Procurement of Quality Assurance Services for the eHRDFS. | 2500000 | 2500000 | Direct Procurement | 2024-05-31 | 2024-06-07 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-12 | 2024-07-19 | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-23 | 2024-08-29 | 2024-09-01 | 2025-06-27 | 2025-04-10
86 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | Business Intelligence & Data Analytics Training externally | 200000 | 200000 | QPP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-01 | 2024-08-30 | 2025-04-10
87 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | Training (Project Management-externally | 200000 | 200000 | QPP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2025-03-31 | 2025-04-10
88 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | Other Developer Recommended Training | 300000 | 300000 | QPP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-01 | 2025-03-31 | As and When
89 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | Publicity/Advertising Expenses e.g Gazetting for System Development & Qualty Assurance Services Project : & e-HRDFS Project Activation Materials | 150000 | 150000 | Micro Procurement | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-01 | 2025-03-31 | 2025-04-10
90 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | Meeting Refreshments/ External Meeting Venue Expenses | 150000 | 150000 | Micro Procurement | As and when | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-01 | 2025-03-31 | 2026-07-12
91 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | High level Capacitation Workshops ( Facilities, Meals, accomodation, transport) | 150000 | 150000 | Micro | As and When | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2025-03-31 | 2025-04-10
92 | Services | Consultancy Services for the Design, development and Implementation of the e-HRDFS. | Actual System Development Costs/Expenses | 8000000 | 8000000 | QPP | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2024-03-25 | 2024-04-04 | 2024-04-08 | 2026-06-03 | 2026-07-12
|  |  | Total eHRDFS | 14740000 | 14740000
Non Credit Bearing Short Courses Unit
93 | Services | Capacity NCBSC Staff on Courses Structure and Quality Assurance. | NCBSC Staff Training (Consutancy services to facilitate training in Gaborone) | 50000 | 50000 | Micro Procurement | 2024-07-05 | N/A | N/A | 2024-07-10 | 2024-07-12 | 2024-07-19 | N/A | N/A | N/A | 2024-07-24 | N/A | N/A | 2024-07-22 | 2024-09-30 | 2024-10-09
94 | Services | Capacitate ETPs on NCBSC Guidelines and Tools (New Entrants) | ETP Capacitation (Internal travel Costs, Accommodation & incidental expenses in Maun, Francistown and Palapye) | 52500 | 52500 | Micro Procurement | 2024-07-29 | N/A | N/A | 2024-07-31 | 2024-08-05 | 2024-08-09 | N/A | N/A | N/A | 2024-08-12 | N/A | N/A | 2024-09-01 | 31/11/2024 | 2024-11-10
95 | Supply | Protective Clothing for NCBSC Officers | Procurement of safety clothing including Branding | 22000 | 22000 | Micro Procurement | 2024-07-05 | N/A | N/A | 2024-07-10 | 2024-07-12 | 2024-07-19 | N/A | N/A | N/A | 2024-07-23 | N/A | N/A | N/A | N/A | 2025-07-30
|  |  | Total NCBSC | 124500 | 124500
Workplace Learning Unit
96 | Supplies | Protective Clothing for WPL Officers | Protective Clothing for WPL Officers | 6000 | 6000 | Micro Procurement | 2024-07-05 | N/A | N/A | 2024-07-10 | 2024-07-12 | 2024-07-19 | N/A | N/A | N/A | 2024-07-23 | N/A | N/A | N/A | N/A | 2025-07-30
97 | Services | WPL Capacity Building Workshop - Francistown | WPL Capacity Building Workshop - Francistown (Transport,Accomodation,Meals for 3 officers, &Venue) | 37500 | 37500 | Micro Procurement | 2024-08-06 | N/A | N/A | 2024-08-08 | 2024-08-09 | 2024-08-12 | N/A | N/A | N/A | 2024-08-13 | N/A | N/A | 2024-09-02 | 2024-09-06 | 2024-09-13
98 | Services | WPL Capacity Building Workshop- Selibe Phikwe | WPL Capacity Building Workshop- Selibe Phikwe (Transport,Accomodation,Meals for 3 officers, &Venue) | 22500 | 22500 | Micro Procurement | 2024-09-02 | N/A | N/A | 2024-09-04 | 2024-09-05 | 2024-09-06 | N/A | N/A | N/A | 2024-09-09 | N/A | N/A | 2024-09-23 | 2024-09-27 | 2024-10-08
99 | Services | WPL Capacity Building Workshop - Tsabong | WPL Capacity Building Workshop - Tsabong (Transport,Accomodation,Meals for 3 officers, &Venue) | 22500 | 22500 | Micro Procurement | 2024-09-23 | N/A | N/A | 2024-09-25 | 2024-09-26 | N/A | N/A | N/A | N/A | 27/09/204 | N/A | N/A | 2024-10-14 | 2024-10-18 | 2024-10-25
100 | Services | WPL Capacity Building Workshop- Kang | WPL Capacity Building Workshop- Kang (Transport,Accomodation,Meals for 3 officers, &Venue) | 22500 | 22500 | Micro Procurement | 2024-10-14 | N/A | N/A | 2024-10-16 | 2024-10-17 | N/A | N/A | N/A | N/A | 2024-10-18 | N/A | N/A | 2024-11-04 | 2024-11-08 | 2024-11-15
101 | Services | WPL Capacity Building Workshop - Hukuntsi | WPL Capacity Building Workshop - Hukuntsi (Transport,Accomodation,Meals for 3 officers, &Venue) | 22500 | 22500 | Micro Procurement | 2024-11-04 | N/A | N/A | 2024-11-06 | 2024-11-07 | N/A | N/A | N/A | N/A | 2024-11-08 | N/A | N/A | 2024-11-25 | 2024-11-29 | 2024-12-06
102 | Services | WPL Capacity Building Workshop - Lobatse | WPL Capacity Building Workshop - Lobatse (Transport,Meals for 3 officers, &Venue) | 21500 | 21500 | Micro Procurement | 2024-11-25 | N/A | N/A | 2024-11-27 | 2024-11-28 | N/A | N/A | N/A | N/A | 2024-11-29 | N/A | N/A | 2024-12-02 | 2024-12-06 | 2024-12-13
103 | Services | Stakeholder Engagement by segregated industries - Maun - Hard to reach Enterprises (HATAB) - Maun 2023 (Transport,Accomodation,Meals for 3 officers, &Venue) | Stakeholder Engagement by segregated industries - Maun - Hard to reach Enterprises (HATAB) - Maun 2023 (Transport,Accomodation,Meals for 3 officers, &Venue) | 16000 | 16000 | Micro Procurement | 2024-04-01 | N/A | N/A | 2024-04-01 | 2024-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2025-04-26 | 2025-05-05
104 | Services | Stakeholder Engagement by segregated industries - Maun - Hard to reach Enterprises (Ghanzi) | Stakeholder Engagement by segregated industries - Maun - Hard to reach Enterprises (Ghanzi) (Transport,Accomodation,Meals for 3 officers, &Venue) | 24000 | 24000 | Micro Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-27 | 2024-08-02
105 | Services | WPL Publications - WPL Adverts ( WSTP's and WPL Workshops) (Publication 6 News Papers) | WPL Publications - WPL Adverts ( WSTP's and WPL Workshops) (Publication 6 News Papers) | 25000 | 25000 | Micro Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-06-16 | 2024-06-21
106 | Services | WPL Publications - WPL Brochure | WPL Publications - WPL Brochure | 10000 | 10000 | Micro Procurement | 2024-06-17 | N/A | N/A | 2024-06-19 | 2024-06-20 | N/A | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | 2024-06-24 | 2024-07-05 | 2024-07-12
107 | Services | TVET - Monitoring and Evaluation of the Implementation of the TVET Action Plan - NTAC | TVET - Monitoring and Evaluation of the Implementation of the TVET Action Plan - NTAC (Meals & Venue for 20 Pax) | 47250 | 47250 | Micro Procurement | 2024-07-02 | N/A | N/A | 2024-07-04 | 2024-07-05 | N/A | N/A | N/A | N/A | 2024-07-08 | N/A | N/A | 2024-07-08 | 2024-07-12 | 2024-07-19
108 | Francistown | Conduct Monitoring and Evaluation to Capacitated Workplaces - Francistown | Conduct Monitoring and Evaluation to Capacitated Workplaces - Francistown (Meals & Accomodation for 3 Officers) | 49900 | 49900 | Micro Procurement | 2025-01-20 | N/A | N/A | 2025-01-22 | 2025-01-23 | N/A | N/A | N/A | N/A | 2025-01-24 | N/A | N/A | 2025-02-03 | 2025-02-07 | 2025-02-14
109 | Selibe Phikwe | Conduct Monitoring and Evaluation to Capacitated Workplaces - Selibe Phikwe | Conduct Monitoring and Evaluation to Capacitated Workplaces - Selibe Phikwe (Meals & Accomodation for 3 Officers) | 30400 | 30400 | Micro Procurement | 2024-02-03 | N/A | N/A | 2025-02-05 | 2024-02-06 | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | N/A | 2025-02-10 | 2025-02-14 | 2025-02-21
110 | Services | Conduct Monitoring and Evaluation to Capacitated Workplaces - Tsabong | Conduct Monitoring and Evaluation to Capacitated Workplaces - Tsabong (Meals & Accomodation for 3 Officers) | 30400 | 30400 | Micro Procurement | 2025-02-17 | N/A | N/A | 2025-02-19 | 2025-02-20 | N/A | N/A | N/A | N/A | 2025-02-21 | N/A | N/A | 2025-02-24 | 2025-02-28 | 2025-03-07
111 | Services | Conduct Monitoring and Evaluation to Capacitated Workplaces - Kang | Conduct Monitoring and Evaluation to Capacitated Workplaces - Kang (Meals & Accomodation for 3 Officers) | 30400 | 30400 | Micro Procurement | 2025-02-24 | N/A | N/A | 2025-02-26 | 2025-02-27 | N/A | N/A | N/A | N/A | 2025-02-28 | N/A | N/A | 2025-03-03 | 2025-03-07 | 2025-03-14
112 | Services | Conduct Monitoring and Evaluation to Capacitated Workplaces - Hukuntsi | Conduct Monitoring and Evaluation to Capacitated Workplaces - Hukuntsi (Meals & Accomodation for 3 Officers) | 30400 | 30400 | Micro Procurement | 2025-02-24 | N/A | N/A | 2025-02-26 | 2025-02-27 | N/A | N/A | N/A | N/A | 2025-02-28 | N/A | N/A | 2025-03-03 | 2025-03-07 | 2025-03-14
113 | Services | Conduct Monitoring and Evaluation to Capacitated Workplaces - Lobatse | Conduct Monitoring and Evaluation to Capacitated Workplaces - Lobatse (Meals & Accomodation for 3 Officers) | 30400 | 30400 | Micro Procurement | 2025-02-24 | N/A | N/A | 2025-02-26 | 2025-02-27 | N/A | N/A | N/A | N/A | 2025-02-28 | N/A | N/A | 2025-03-10 | 2025-03-14 | 2025-03-21
|  |  | Total WPL Unit | 448750 | 448750
|  |  | Total Department of Funding | 1670973 | 16410973

## DHR (hidden)
Procuring Department
DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activiry Report
Services
| Skills Gap Assesment |  | 150000 |  | RFQ | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-04-09
| Engagement Survey |  | 50000 |  | RFQ | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-04-09
| Implementation of culture change |  | 300000 |  | Direct procurement |  |  |  | 2024-04-01 | 2024-04-26 | 2024-05-10 | 2024-05-17 | 2024-05-17 | 2024-04-24 | 2024-04-25 |  | 2024-05-08 | 2024-04-01 | 2024-10-01 | 2024-11-08
| Staff Training & Development | [16 empty] | 2024-04-01 | 2025-05-31 | 2025-06-07
| Capacity Building |  | 650000 |  | RFQ | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-05-31 | 2025-06-07
| Proffessional Membership Sbscriptions & CPDs |  | 300000 |  | Direct Procuremet | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-03-31
| Longterm Training |  | 550000 |  | Direct Procuremet | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-04-09
[9 empty] | N/A | N/A
| Staff Welfare |  | 570000 |  | RFQ | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-04-09
| Pension Fund Management |  | 120000 |  | ITT | 2024-04-01 |  |  |  |  | 2024-04-01 | 2024-04-19 | 2024-04-26 |  |  |  |  | 2024-04-01 | 2025-03-31 | 2025-04-09
| Union Meetings |  | 60000 |  | RFQ | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-04-09
| Recruitment |  | 200000 |  | RFQ | N/A | N/A | N/A | N/A | N/A | [7 empty] | 2024-04-01 | 2025-03-31 | 2025-04-09

## Marketing (hidden)
DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | HATAB Conference | Hatab Conference( Travel, accomodation, meals and conference fee) | 27150 | 27150 | Micro Procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-04-25 | 2024-04-26 | 2024-05-03
Services | Botswana Consumer Fair | Botswana Consumer Fair ( stall branding and meals) | 72000 | 72000 | Micro Procurement | 2024-08-01 | 2024-08-02 | N/A | 2024-08-05 | 2024-08-07 | 2024-08-09 | 2024-08-12 | 2024-08-14 | 2024-08-15 | 2024-08-19 | 2024-08-20 | 2024-08-22 | 2024-08-27 | 2024-09-03 | 2024-09-11
Service | Botswana Global Expo | Botswana Global Expo ( stall branding and meals) | 72000 | 72000 | Micro Procurement | 2024-09-09 | 2024-09-10 | N/A | 2024-09-12 | 2024-09-13 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-23 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-10-09 | 2024-10-11 | 2024-10-18
Services | Trade Up North Expo | Trade Up North Expo ( stall branding, travel accomodation and meals) | 21600 | 21600 | Micro Procurement | 2024-07-01 | 2024-07-01 | N/A | 2024-07-03 | 2024-07-09 | 2024-07-10 | 2024-07-12 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-25 | 2024-07-26
Services | Digital Marketing (Social Media Management) | Digital Marketing (Social Media Management) | 220000 | 220000 | Micro Procurement | 2024-05-01 | 2024-05-03 | N/A | 2024-05-06 | 2024-05-13 | 2024-05-15 | 2024-05-20 | 2024-05-22 | 2024-05-23 | 2024-05-27 | 2024-05-28 | 2024-05-30 | 2024-06-03 | 2024-11-04 | 2024-11-11
Services | Print Media Campaign | Print Media Campaign - (advertising and publications) | 150000 | 150000 | Micro procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-05-01 | 2025-03-31 | 2025-04-01
Services | Radio Campaign | Radio Campaign - (advertising) | 50000 | 50000 | Micro Procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-05-01 | 2025-03-31 | 2025-04-01
Services | Television | Television advertising- (advertising) | 50000 | 50000 | Micro Procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-05-01 | 2025-03-31 | 2025-04-01
Services | Outdoor Advertising | Outdoor Advertising - (advertising on bill boards) | 50000 | 50000 | Micro Procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-05-01 | 2025-03-31 | 2025-04-01
Supplies | Board Promotional Materials | Board Promotional Materials | 100000 | 100000 | Micro Procurement | 2024-07-01 | 2024-07-03 | N/A | 2024-07-04 | 2024-07-12 | 2024-07-16 | 2024-07-19 | 2024-07-22 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-29 | 2024-07-31 | 2024-08-12 | 2024-08-19
Supplies | Staff Promotional Materials | Staff Promotional Materials | 200000 | 200000 | Micro Procurement | 2024-07-01 | 2024-07-03 | N/A | 2024-07-04 | 2024-07-12 | 2024-07-16 | 2024-07-19 | 2024-07-22 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-29 | 2024-07-31 | 2024-08-12 | 2024-08-19
Supplies | General Promotional Materials | General Promotional Materials | 100000 | 100000 | Micro Procurement | 2024-07-01 | 2024-07-03 | N/A | 2024-07-04 | 2024-07-12 | 2024-07-16 | 2024-07-19 | 2024-07-22 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-29 | 2024-07-31 | 2024-08-12 | 2024-08-19
Supplies | CSR Projects | CSR Projects - (stationery support, travel, accomodation) | 200000 | 200000 | Micro Procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-05-01 | 2025-03-31 | 2025-04-01
Services | Annual Report | Annual Report - (Design and printing) | 44000 | 44000 | Micro Procurement | 2024-08-01 | 2024-08-02 | N/A | 2024-08-05 | 2024-08-12 | 2024-08-14 | 2024-08-15 | 2024-08-19 | 2024-08-20 | 2024-08-22 | 2024-08-27 | 2024-08-28 | 2024-09-02 | 2024-09-09 | 2024-09-16
Services | HRDC Corporate Profile | HRDC Corporate Profile - (Printing) | 33000 | 33000 | Micro Procurement | 2024-08-01 | 2024-08-02 | N/A | 2024-08-05 | 2024-08-12 | 2024-08-14 | 2024-08-15 | 2024-08-19 | 2024-08-20 | 2024-08-22 | 2024-08-27 | 2024-08-28 | 2024-09-02 | 2024-09-09 | 2024-09-16
Services | Workplace Brochure | Workplace Brochure -( Printing) | 5000 | 5000 | Micro Procurement | 2024-08-01 | 2024-08-02 | N/A | 2024-08-05 | 2024-08-12 | 2024-08-14 | 2024-08-15 | 2024-08-19 | 2024-08-20 | 2024-08-22 | 2024-08-27 | 2024-08-28 | 2024-09-02 | 2024-09-09 | 2024-09-16
Supplies | Re-Prints | Re-Prints | 100000 | 100000 | Micro Procurement | 2024-04-01 | 2024-04-03 | N/A | 2024-04-05 | 2024-04-08 | 2024-04-10 | 2024-04-12 | 2024-04-15 | 2024-04-17 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-05-01 | 2025-03-31 | 2025-04-01
|  | TOTAL | 1494750 | 1494750
Total

## Oversight (hidden)
No | DISCIPLINE | Project Description | Project Activity | Budget Amount BWP | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
1 | Services | Capacity Building Training | Capacity Building Training- Procurement of facilitator, and conference facility) | 200000 | 300000 | Direct procurement/Micro Procurement |  | N/A | N/A | 2024-04-01 | 2024-04-04 | 2024-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-06-05 | 2024-06-12
Total |  |  |  | 200000 | 300000

## BS (hidden)
DISCIPLINE | Project Description | Project Activity | 0 | Estimated Cost BWP | Method of Procurement | Preparation of ITT (inc TORs & Market Research ) | Submission of ITT to POU for vetting | Date of Intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by evaluation committee | Verification of Evaluation Report by PU | Submission of Evaluation Report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of Project Implementation | Completion of project Implementaion | End of Activity Report
Services | Board Evaluation | Board Evaluation Services | P150 000 | P150 000 | QPP | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | N/A | 2024-06-06 | 2024-06-17 | 2024-06-28 | 2024-07-12
| Board Induction | Board Induction ( Conference facility) | P30 000 | P50 000 | Micro Procurement | 2024-05-10 | N/A | N/A | 2024-05-13 | 2024-05-15 | 2024-05-16 | N/A | N/A | N/A | 2024-05-20 | N/A | 2024-05-21 | 2024-05-22 | 2024-05-22 | 2024-05-30
| Board Training | Board Training(flights, accomodation, perdiem) | P300 000 | P691 000 | Micro Procurement | 2024-08-01 | 2024-08-07 | N/A | 2024-08-12 | 2024-08-19 | 2024-08-23 | 2024-08-27 | N/A | N/A | 2024-09-05 | N/A | N/A | 2024-09-16 | 2024-09-20 | 2024-09-30
| Board Retreat | Procurement of conference facility, transport, accomodation and meals | P184 000 | P150 000 | Micro Procurement | 2024-06-03 | N/A | 2024-06-05 | N/A | 2024-06-10 | 2024-06-14 | N/A | N/A | N/A | 2024-07-02 | N/A | 2024-07-08 | 2024-07-15 | 2024-05-19 | 2024-07-30